## Master_Schedule_1
Category | MileStone | Task | Zone 1 | Zone 2 | Zone 3.3 | Zone 3.4
KPI | PLC Tags | PLC Tags - OK, NOK, MachineStatus related Tags | NA | Received | Received | Received
|  | PLC Tags- Alarm & Descriptions |  | Received | Received | Received
|  | PLC Tags - Cycle Time |  | Received | Received | Received
|  | PLC Tags - Rejection & Description |  | Received | Received | Received
|  | PLC Tags - Losses & Description |  | Received | Received | Received
|  | PLC Tags - Rework |  | Received | Received | Received
| Kepware | Kepware Config - OK, NOK, MachineStatus related Tags |  | Completed | Completed | Completed
|  | Kepware Config - Alarm & Descriptions |  | Completed | Completed | Completed
|  | Kepware Config - Variant & Cycle Time |  | Inprogress 30-Sep-24 | Inprogress 30-Sep-24 | Inprogress 30-Sep-24
|  | Kepware Config - Rejection & Description |  | Completed | Completed | Completed
|  | Kepware Config - Losses & Description |  | Completed | Completed | Completed
|  | Kepware Config - Rework |  | Completed | Completed | Completed
| Portal Settings | Portal Settings - Alarm, Rejection , Losses |  | Completed | Completed | Completed
|  | Portal Settings - Variants & Cycle Time |  | Inprogress 30-Sep-24 | Inprogress 30-Sep-24 | Inprogress 30-Sep-24
| MIS Report | MIS Validation with RawTable data ( Internal) |  | Completed
|  | MIS FeedBack on Pages Features |  | 2024-09-30
|  | PLC Team discussion on Production Validation |  | Yet to Start 08-Oct-2024 | Yet to Start 10-Oct-2024 | Yet to Start 13-Oct-2024
| Zone Validation | Validation with Production |  | Yet to Start 08-Oct-2024 | Yet to Start 10-Oct-2024 | Yet to Start 13-Oct-2024
| Security | Security IT Guideline (VAPT) receipt and DNS |  | 2024-10-10
|  | Manual MIS (Daywise and Stationwise) |  | 2024-10-10
| Session Handling | Portal Session expiry to be handled |  | 2024-10-10
| Performance | Performance Report for KPI |  | 2024-10-03
Performance Report for ZoneDashboard
CBM | PLC Tags | PLC Tags - Servo | Received | Received | Received | Received
|  | PLC Tags - VFD | Received | Received | Received | Received
|  | PLC Tags - Energy Meteer | Received | Received | Received | Received
|  | OP3020A - Both 2 servo to be considered OP3020B - Both 2 servo to be considered | NA | NA | Yet to Recieve Tags 30-Sep-24 | Yet to Recieve Tags 30-Sep-24
| Kepware | Kepware Config - Servo | Completed | Completed | Completed | Completed
|  | Kepware Config - VFD | Completed | Completed | Completed | Completed
|  | Kepware Config - Energy Meteer | Completed | Completed | Completed | Completed
|  | Kepware Config - 2 servos | NA | NA | Yet to Start 03-Oct-2024 | Yet to Start 03-Oct-2024
| Portal Settings | CBM Portal Settings | Completed | Completed | Completed | Completed
|  | Settings for 2 servos | NA | NA | Yet to Start 03-Oct-2024 | Yet to Start 03-Oct-2024
|  | Feedback Points Resolving | Inprogress 01-Oct-24 | Inprogress 01-Oct-24 | Inprogress 01-Oct-24 | Inprogress 01-Oct-24
|  | Live Button for CBM in Icons Section ( before Historic Icon)- Mail Confirmation & Development | Yet to Start 01-Oct-24
| CBM Mail alerts | Feedback Points | 2024-10-04
i4metrics Portal | Demo | Demo to Customer -1 | 2024-10-15
i4metrics Documents | Documentation | User manual | Completed
|  | IIS | Completed
|  | Kepware Tag Configuration | Completed
|  | Service Documentation | Completed
IIOT Prod Migration | Prod Server Movement | Prod Server Movement | TBD | TBD | TBD | TBD
Commissioning Plan |  |  |  |  | Production Run | Non Production
KPI & MIS Report | Validation Zone 2 | 2024-10-08 | 2024-10-09 | Akash , Pavithra | OK, NOK, Losses ,CT Rejection , Alarm, Losses, Rework , Machine Status | Rework, Machine Status, Dry Run, OK, NOK, CT, Alarm
| Validation Zone 3.3 | 2024-10-10 | 2024-10-11 | Akash , Pavithra | OK, NOK, Losses ,CT Rejection , Alarm, Machine Status | Rework, Machine Status, Dry Run, OK, NOK, CT, Alarm
| Validation Zone 3.4 | 2024-10-12 | 2024-10-13 | Akash , Pavithra | OK, NOK, Losses ,CT Rejection , Alarm, Machine Status | Rework, Machine Status, Dry Run, OK, NOK, CT, Alarm
CBM | Validation Zone 1 | 2024-10-08 | 2024-10-08
| Validation Zone 2 | 2024-10-08 | 2024-10-09
| Validation Zone 3.3 | 2024-10-10 | 2024-10-11
| Validation Zone 3.4 | 2024-10-12 | 2024-10-13 | Yet to be configured in Kepware
Priority -1 | OK, NOK, Total Count, CT, Machine Status ,Alarm | HMI --> Kepware | Akash / Pavithra
| OK, NOK, Total Count, CT, Machine Status ,Alarm | Kepware --> DB RawTables | Akash / Pavithra
Priority -2 | Losses , Reject , Rework | HMI --> Kepware | Akash / Pavithra
| Losses , Reject , Rework | Kepware --> DB RawTables | Akash / Pavithra

## Pending Tags Status
Task | Zone 2 | Zone 3.3 | Zone 3.4
Rejection Tags | Recieved | Recieved | Recieved
Kepware Configuration - Rejection | Completed | Completed | Completed
Portal Settings - Rejection | Completed | Completed | Completed | Task List | Responsible | Status | Target Date
Alarm Tags | Recieved | Recieved | Recieved | SSO POC - Gmail | Vishnupriya | Completed | 2024-09-19
Kepware Configuration - Alarm | Completed | Completed | Completed | SSO POC - Azure | Vishnupriya | Completed | 2024-09-19
Portal Settings - Alarm | Completed | Completed | Completed | Portal Settings | Vishnupriya | Completed | 2024-09-23
Rework Tags | Recieved | Recieved | Recieved | Rework Changes in Gateway | Veera | Inprogress | 2024-09-25
Kepware Configuration - Rework | Yet to Start | Yet to Start | Yet to Start | Losses Configuration | Veera | Inprogress | 2024-09-25
Portal Settings - Rework | Yet to Start | Yet to Start | Yet to Start | CBM Portal Issue Fixes | Lekshmi | Inprogress | 2024-09-26
Losses Tags | Recieved | Recieved | Recieved | CBM Zone 3.4 Tag Configuration | Lekshmi | Yet to Start | 2024-09-26
Kepware Configuration - Losses | Yet to Start | Yet to Start | Yet to Start | Kepware tag configuration - Updated tag address | Lekshmi | Yet to Start | 2024-09-26
Portal Settings - Losses | Completed | Completed | Completed | Session TimeOut to be removed in KPI Application | Vishnu | Yet to Start | 2024-10-04
Variant Tags | Recieved | Recieved | Recieved | MIS Validation with Actual EOL Stations | Veera, Anne , Vishnu | Yet to Start | 2024-10-04
Kepware Configuration - Variant | Yet to Start | Yet to Start | Yet to Start | CBM Instant and Summary Mail - Validation | Subramani , Lekshmi | Yet to Start | 2024-10-04
Portal Settings - Variant ( 4 Variants ) | Completed | Completed | Completed | Zone 2 Validation | Veera, Anne , Vishnu | Yet to Start | 2024-10-10
|  |  |  | Zone 3.3 Validation | Veera, Anne , Vishnu | Yet to Start | 2024-10-10
|  |  |  | Zone 3.4 Validation | Veera, Anne , Vishnu | Yet to Start | 2024-10-10
CBM Task | Zone 2 | Zone 3.3 | Zone 3.4 | CBM Zone 1 Validation | Lekshmi | Yet to Start | 2024-10-10
Abnoraml Value Correction | Completed | Completed | Completed | CBM Zone 2 Validation | Lekshmi | Yet to Start | 2024-10-10
Kepware Configuration | Completed | Completed | Yet to Start | CBM Zone 3.3 Validation | Lekshmi | Yet to Start | 2024-10-10
Portal Settings | Completed | Completed | Yet to Start | CBM Zone 3.4 Validation | Lekshmi | Yet to Start | 2024-10-10
Bug Fixes | Inprogress | Inprogress | Inprogress

## Tags Status from PLC (hidden)
HMCL MileStones of i4metrics
KPI Portal
Development of KPI Usecases | Completed
Development of Customized Dashboard to HMCL - ZoneDashboard | Completed
KPI Demo 1 to Customer | Completed
KPI Demo 2 to Customer | Yet to give Demo : 12-Sep-2024 Tags to be recieved by : 5-Sep-2024 6-Sep-2024 | Rejection, Rework , Updated Alarm List, Variant , Loseses to be give as Demo once we recieve Tags from PLC
CBM Portal
Important Features in CBM | Completed
Advanced features finetuning | 2024-09-05
CBM Demo 1 to Customer | Completed
CBM Demo 2 to Customer | Yet to give Demo: 5-Sep-2024 9-Sep-2024 Corrected Tags values to be mapped by :2-Sep-2024 6-Sep-2024 | Some CBM Tags are showing very high values which needs to be discussed with Suppliers by PLC team & the corrected tags to be provided
MIS Report
MIS Report Demo 1 | Completed | Mail will be generated to all Department Heads in HMCL on 29th Aug 2024
MIS Report Demo 2 | Yet to give Demo: 12-Sep-2024 | Will include Feedback from Customer
Tasks | Status
Tag receipt with proper values in PLC-6-Sep-2024 | Rejection Code & Description - Zone 2, Zone 3.3 , Zone 3.4 --Received. Alarm Tags - Zone 2, 3.3 & 3.4 --Received. Rejection Tags working needs to be validated along PLC Programmer. Latest Alarm Description for Zone 2, 3.3 , 3.4 --Recieved. Rework Tags -- Mapping in PLC and give tags by Sep16 for all Zones.--Recieved PLC programmer was on Leave , will share by tomorrow (Sep 17). Cycle time Mapping - To be implemented (Logic explained to Karuppasamy , Prasanna , Rizwan). Kindly find the trailing mails for the Stations where Logic is yet to be implemented Variant Code Tag --Yet to Validate. Error Active is ON but no values is shown in Alarm word Tags. OP3030, OP3140 - Zone 3.3 - Now Working Fine. Alarm OP4130, OP4140, OP4120 - Zone 3.4 - Recieved. Losses (Description & Tags) for Zones 2 - Recieved. Losses(Description & Tags) for Zone 3.3 , 3.4 - Recieved
CBM Abnormal Values Meeting with Supplier | 16-09-2024 - Screenshots was shared again to Karuppasamy. 17-09-2024 - Will connect with Festo Supplier.
Demo of KPI/CBM and Zonewise Dashboard -16-Sep-2024 | Yet to Show Demo
Conclusion Email 1-20-Sep-2024 | Yet to Show Demo
Production DB and application deployment-?? | Only after proving 100 Battery Packs to be proved in Production access will be proviced
Production Server for OPC UA -?? | Only after proving 100 Battery Packs to be proved in Production access will be proviced
CBM abnormal values checking -7-Sep-2024 | As per PLC Comments : "We observed some parameters are abnormal or N/A in drive itself. I'm attaching screenshot for your reference. Kindly discuss with supplier for any queries. "
IT guideline for vulnerability | 07-09-2024 Kamal will schedule a meeting
SSO implementation | 07-09-2024 Kamal will schedule a meeting
DNS implementation | 07-09-2024 Kamal will schedule a meeting
Conclusion email2 - 06-oct-2024 | Yet to Show Demo
MileStone | MileStones | Status | Target Dates
PLC Tags | KPI Pending Tags | Cycle Time, Loss Code and Description , Rejection Code and Description , Rework, Alarm , Updated / New PLC address , Variant Code and Description For all Zones
| CBM Tags | high values which needs to be discussed with Suppliers by PLC team & the corrected tags to be provided
ZoneDashboard | ZoneDashboard Test Run 2 | Inprogress
| ZoneDashboard Modifications | Yet to Start
CBM Portal | CBM Portal Bug fixes | Inprogress
| CBM Guidelines to be implemented | Yet to Start
| CBM Test Run 2 | Yet to Start
| CBM Tag Configuration for Typewisse and Category | Yet to Start
| CBM Mailer for Instant and Overall Mail | Inprogress
MIS Report | MIS Report Test run 2 | Inprogress
| MIS Report Modifications | Yet to Start
| MIS Mail Recipients for Prod , Quality , Maintenance | Completed
KPI Zone 3.4 and Pending Tags Validation | Validation of Pending tags | Cycle Time, Loss Code and Description , Rejection Code and Description , Rework, Alarm , Updated / New PLC address , Variant Code and Description For all Zones

## HMCL_CheckList
CheckList for HMCL
KPI | Status | Remarks
Zone 2 KPI Dashboards | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
Zone 3.3 KPI Dashboards | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
Zone 3.4 KPI Dashboards | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
MIS Report for Zone 2 | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
MIS Report for Zone 3.3 | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
MIS Report for Zone 3.4 | ü | Portal features working , Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
KPI Operation Manual | ü | Portal features Documentation done. Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
SOP for Webjobs | ü | Portal features Documentation done. Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
SOP for Portal Hosting | ü | Portal features Documentation done. Yet to recieve Rejection, rework, Variant,Cycle Time, Alarm List , Losses Tags from PLC
CBM | Status | Remarks
Zone 1 CBM Sensors | ü | Portal Configuration in Completed
Zone 2 CBM Sensors | ü | Energy Meter to be added
Zone 3 CBM Sensors | ü | Energy Meter to be added
Alarm Mails - Instant Mail | ü | New API Development - Completed Keeping in View of HMCL Architecture
Alarm Mails - OverAll Mail | ü | New API Development - InProgress Keeping in View of HMCL Architecture
CBM Services Nodejs replaced by CBM Service API in Application Server | ü | New API Development - Completed Keeping in View of HMCL Architecture
CBM Operation Manual | ü | Completed
SOP for CBM Mail Hosting | InProgress | InProgress

## PLC IP & IP Details
Server IP Details
Portal | OPC UA Server IP | Application Server IP | DB Instance
KPI | 192.168.101.106 | 10.79.3.37 | 10.79.3.34,3534
CBM | 192.168.101.106 | 10.79.3.37 | 10.79.3.34,3534
HMCL Zone PLC IP:
Zone 2 PLC - 172.18.40.215,
Zone 3.3 PLC1 - 172.18.40.43,
Zone 3.3 PLC2 : 172.18.40.45,
Zone 3.4 PLC 1 : 172.18.40.47.255
Zone 3.4 PLC 2 : 172.18.40.49.255
DB Server:
Host Name:
10.79.3.34,
Port Number : 3534
Login: BPATEAL
password : TEAL@2024!
Application VM :
IP : 10.79.3.37
user name : he6cbpascada@hero_motocorp.com
pswd : A1b2c3!@#
IIS Port Number : 81
OPCUA Server
IP : 192.168.101.106
user name : he6cbpadb@hero_motocorp.com
pswd : A1b2c3!@#$

## Milestone_HMCL
Type | Cateogory | Deliverable | Milestone/task | Responsibility | % Pending | Target Date | Risk
Milestone | KPI | Gateway Service | OPC server pc setup | TEAL+HMCL
|  |  | OPCUA server pc accessing using VPN | Mani | 0% | 13/05/2024 | SCADA & IOT team need to access same Server pc through RDP(only via shopfloor pc)
|  |  | Gateway service code backup movement | Akash+Vishnu | 0% | 2024-10-05
|  |  | Gateway service & PLC service code configuration - Zone 3.3 | Anne+veera | 20% | 22/05/2024 | W.r.t tag recieved tag to be configure in service to avoid unwanted data posting
|  |  | Gateway service & PLC service code configuration - Zone 3.4 | Anne+veera | 20%
|  |  | Gateway service & PLC service code configuration - Zone 2 | Anne+veera | 20% | 25/05/2024 29/05/2024 05/06/2024 | Delayed due to PLC mapping(engaged with machine activities) Tag recieved,alarm description pending (OP100 & OP20A some tag not binded)
|  |  | Kepware configuration & tag configuration | Anne+veera | 20% | 25/05/2024
|  |  | Offline tag preparation(CSV format) | Anne+veera | 0% | 25/05/2024
|  |  | Internet provision & Dependency library package installation | Veera+Mani | 0% | 15/05/2024 | If any packages to be install or troubleshoot with internt pc should move to HMCL server room and need to get support from mani for internet and installing
|  |  | OPCUA server communicating with DB server pc | Mani | 0% | 17/05/2024 | Firewall to be enable from HMCL team(Mani)
|  |  | Internet access provided for TEAL laptop | Mani | 0% | 15/05/2024
|  |  | Target parts per shift, per hour need to get from HMCL | TEAL+HMCL | 0% | 25/05/2024 | Yet to discuss with HMCL team Kamal has asked TEAL team to calculate based on CT
|  |  | Gateway service realiability | TEAL | 0% | 30/06/2024 | Kamal has asked TEAL team to calculate based on CT
|  |  | Gateway service all setup again installation after 500 parts running | TEAL+HMCL | 100% | TBD
|  |  | Need to setback to original infomration where hardcoded in gateway service | TEAL | 50% | TBD | Shift will reamian Hardcoded Variant Info - will be synced and made Dynamic
|  |  | Kepware issue raised(duplicate value binding in tag for z3.3 plc2) | TEAL+Kepware | 0% |  | Issue raised with kepware team on 05/06/2024 Netwrok issue - Root cause
|  |  | PM2 configured in OPCUA pc | TEAL | 0% | 2024-05-06 | Need observation
|  |  | PM2 observation for automatically service start on daily | TEAL | 40% | 15/06/2024 | Under observation right now
Milestone | KPI | Gateway Service | Gateway service connectivity to DB(HMCL) | TEAL+HMCL
|  |  | DB configuration in gateway service | Anne+veera | 0% | 15/05/2024 | Completed
|  |  | DB creation & schema script running | Vishnu+Anne | 0% | 15/05/2024 | Completed
|  |  | DB connectivity with gateway service | Veera+Mani | 0% | 17/05/2024 | Got support from mani for accessing dg through program
|  |  | Support from HMCL(mani) for DB connectivity | veera+vishnu | 0% |  | Completed
|  |  | Station identification & configuring in station list | Veera | 0% | 21/05/2024 | Identifying required station to eliminate logging
Milestone | KPI | PLC tag reciept | PLC reciept for zone 3.3 & 3.4 | TEAL-PLC&IOT
|  |  | Production tag ,Alarm,loss,rejection& machine status tags reciept | Karuppasamy&Team | 40% | 23/05/2024 | loss, rejection yet to map
|  |  | Alarm description | Karuppasamy&Team | 10% | 25/05/2024 | Alarm description will keep on update as per machine running daily
|  |  | Loss description | Karuppasamy&Team | 30% | 25/05/2024 | Yet to mapped
|  |  | Rejection description | Karuppasamy&Team | 50% | 25/05/2024 | Rejection reason logic not implemented in plc logic(HMCL & TEAL team yet to confirm)
|  |  | Mapping all tags & descirptions | Karuppasamy&Team | 20% | 25/05/2024 | Tags provided but mapping pending
|  |  | Tag validation | Pavithra+Anne | 20% | 28/05/2024
Milestone | KPI | PLC tag reciept | PLC reciept for zone 2 | TEAL-PLC&IOT
|  |  | Production tag ,Alarm,loss,rejection& machine status tags reciept | Karuppasamy&Team | 20% | 25/05/2024 29/05/2024 | loss, rejection yet to map
|  |  | Alarm description | Karuppasamy&Team | 70% | 25/05/2024 29/05/2024 06/06/2024 | Alarm description will keep on update as per machine running daily
|  |  | Loss description | Karuppasamy&Team | 50% | 25/05/2024 29/05/2024 TBD
|  |  | Rejection description | Karuppasamy&Team | 50% | 25/05/2024 29/05/2024 TBD | Rejection reason logic not implemented in plc logic(HMCL & TEAL team yet to confirm)
|  |  | Mapping all tags & descirptions | Karuppasamy&Team | 30% | 25/05/2024 29/05/2024 | Tags provided but mapping pending
|  |  | Tag validation | Pavithra+Anne | 30% | 25/05/2024 29/05/2024
Milestone | KPI | PLC tag reciept | PLC reciept for zone 1 | TEAL
|  |  | Production tag ,Alarm,loss,rejection& machine status tags reciept | Karuppasamy&Team | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
|  |  | Alarm description | Karuppasamy&Team | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
|  |  | Loss description | Karuppasamy&Team | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
|  |  | Rejection description | Karuppasamy&Team | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
|  |  | Mapping all tags & descirptions | Karuppasamy&Team | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
|  |  | Tag validation | Pavithra+Anne | 100% | TBD | IIOT will not consider Zone 1 considering battery cells
Milestone | KPI | Database service | Database server pc setup | TEAL+HMCL
|  |  | DB server pc accessing through VPN | Mani | 0% | 23/05/2024 | DB accessing only though SSMS(cant access DB server pc through Remote desktop) Have shared all the data to HMCL Team and it is in the plate of HMCL HR Team
|  |  | Details providing for VPN accessing | Angu+veera | 0% | 15/05/2024
|  |  | Schema script movement to mani | Vishnu+Anne | 0% | 16/05/2024 | Completed
|  |  | DB username & password | Mani | 0% | 16/05/2024 | Completed
|  |  | Firewall setup for accessing DB though ssms(TEAL Laptop) | Mani | 0% | 16/05/2024 | Completed
|  |  | DB server pc reliability | Vishnu+Mani | 90% | 30/05/2024 | Need to observe daily/weekly/monthly basis storage increase Need to observe CPU,RAM usage
|  |  | TEAL firewall rule update for VPN connection | TEAL IT | 50% | 30/05/2024 | Ticket raised with TEAL IT team for Zscaler rule update
|  |  | KPI Script movement | Completed | 0%
|  |  | CBM Script movement | Completed | 0%
|  |  | DB Utilisation and memory utilisation monitoring | Completed | 0%
|  |  | DB port enabling for Application server and OPC Server | Completed | 0%
Milestone | KPI | Application service | Application server pc setup | TEAL+HMCL |  |  | Completed
|  |  | Application PC Access using VPN | Mani | 0% | 2024-05-23
|  |  | TEAL firewall rule update for VPN connection | TEAL IT | 0% | 30/05/2024 | Ticket raised with TEAL IT team for Zscaler rule update
|  |  | Listed Activities in Application server , shared with Kamal and Mani | Mani and Kamal | 0% | 15/05/2024 | Completed
|  |  | Getting Application Server credentials from HMCL | Mani and Kamal | 0% | 15/05/2024 | Completed
|  |  | Creating the Application pool and mapping to the application | Vishnu | 0% | 15/05/2024 | Completed
|  |  | providing the Permission IIS_IUSRS and IUSR to the hosted folder | Vishnu+Anne | 0% | 15/05/2024 | Completed
|  |  | Providing Access to DB user so that Applications work | Mani | 0% | 16/05/2024 | Completed
|  |  | Downloading the Source code for Frontend ,API's and manual API - if GITHUB access provided | Vishnu + Mani ( github access providing ) | 40% | NA | VS installation completed , but git access needed or any share folder req to move code....
|  |  | Set up of Frontend Solution in VS | Vishnu | 100% | NA | As of Now working in Local and moving Publish Folder to Application Server
|  |  | Set up of Live API Solution in VS | Vishnu | 100% | NA | As of Now working in Local and moving Publish Folder to Application Server
|  |  | Set up of Historic API Solution in VS | Vishnu | 100% |  | As of Now working in Local and moving Publish Folder to Application Server
|  |  | Publish - Front end solution ( if VS and GIT access not available ) | Vishnu | 0% | 16/05/2024 | Completed
|  |  | Publish - Live end solution ( if VS and GIT access not available ) | Vishnu | 0% | 16/05/2024 | Completed
|  |  | Publish - Historic end solution ( if VS and GIT access not available ) | Vishnu | 0% | 16/05/2024 | Completed
|  |  | Verifying Portal Working and functioning in VS before Hosting | Vishnu + Anne | 0% |  | Completed
|  |  | Frontend Solution hosting the code in IIS | Vishnu | 0% | 17/05/2024 | Completed
|  |  | Historic Api Solution hosting code in IIS | Vishnu | 0% | 17/05/2024 | Completed
|  |  | Live Api Solution hosting code in IIS | Vishnu | 0% | 17/05/2024 | Completed
|  |  | Portal Modifications | Vishnu | 20% | 2024-07-26 | UI and data validations , modifications will be made
|  |  | Portal Settings and Configurations | Vishnu + Anne | 20% | 22/05/2024 | Based on kepware configurations of stations and descriptions recieving from PLC we'll update
|  |  | Manually inserted in all tables and checking all chart | Anne+pavithra | 0% | 20/05/2024 | Completed
|  |  | Listing portal bug w.r.t manual insert data | Anne+vishnu | 0% | 20/05/2024 | Completed
|  |  | Customer Mail ID for Sharing MIS with Customer | Kamal | 100% | 24/05/2024 | Need Mail ID to sent MIS reports to Customer
|  |  | HMCL Shift Timings for Production | Kamal | 100% | 24/05/2024 | Need shift timings for Batterpack Line from HMCL
|  |  | MIS report Code modifications based on requirement of Zones 3.3 | Santu | 5% | 23/05/2024 | Validation completed , bugs to be resolved
|  |  | MIS Report Code modification for Zone 3.4 | Santu | 5% | 25/05/2024 | Validation completed , bugs to be resolved
|  |  | MIS Report Code modification for Zone 2 | Santu | 5% | 25/05/2024 | Validation completed , bugs to be resolved
|  |  | Zone Dashboard devlopment | Vishnu | 0% | 2024-02-06 | Completed
|  |  | MIS task creation | Vishnu | 0% | 21/05/2024 | Completed
|  |  | MIS report webjob creation | Santu | 0% | 27/5/2024 | Completed
|  |  | Webjobs Timings as per HMCL shift timings | Veera/Sankar | 5% | 27/5/2024 | Completed as of now 10.30 mail is generated
|  |  | MIS mail generation and validation | Vishnu + Anne | 0% | 29/5/2024 | Completed
|  |  | Validating Portal after Settings | Vishnu+Anne | 0% |  | Completed
|  |  | Task Scheduler Creating task for: 1.RejectionReason 2.webjob_AvailOEE_Live 3.webjob_CycletimeHistoric 4.Hourly tracker ( Test 119) 5.DB Optimisation | Vishnu | 0% | 2024-12-05 | Completed
|  |  | Adding jobs to task schedular | Vishnu | 0% | 13/05/2024 | Completed
|  |  | Scheduling the task in the task schedular | Vishnu | 0% | 13/5/2024 | Completed
|  |  | Providing the Permission to the task schedular | Vishnu | 0% | 17/5/2024 | Completed
|  |  | Testing the task | Vishnu | 0% | 18/05/2024 | Completed
|  |  | Browsing the Portal and checking the pages for the data arriving | Vishnu | 20% | Continuous Process | Rejection , Rework , Losses pages are yet to be recieved
|  |  | User role creation for the HMCL user | Vishnu | 0% | 2024-06-03
|  |  | SMTP Details for Sending MIS Report in Mails to HMCL cutomer | Vishnu + Kamal | 0% | 2024-06-14 | Completed
|  |  | DNS to be get from HMCL team for defining final portal URL with HTTPS | Vishnu+Mani | 100% | TBD | Yet to Confirm if HMCL will provide SSL and DNS info for Production Portal
Milestone | CBM | CBM Service Setup | CBM services in OPC Server | TEAL+HMCL
|  |  | CBM Service and OPCUA Client service Latest code Movement to OPC Server | Akash,Subramani, Lekshmi | 0% | 2024-07-17 | Completed
|  |  | Configuration of DB credentials in CBM service | Akash,Subramani, Lekshmi | 0% | 2024-07-17 | Completed
|  |  | Enabling port 7004 to communicate with IT Layer | Vishnu + Mani | 0% | 2024-07-17 | Completed
|  |  | Tags for Zone 2 and Zone 3.3 from PLC | Karuppasammy | 0% | 2024-07-17 | Completed
|  |  | Kepware configuration of CBM Zone 2 and Zone 3.3 Tags | Veera + Lekshmi | 0% | 2024-07-17 | Completed
|  |  | Portal Pages validation CBM for Zone 2 and Zone 3.3 | Pavithra + Lekshmi | 0% |  | Completed
|  |  | Zone 1 CBM Tags | Karuppasammy | 0% | 2024-07-22 | Completed
|  |  | Kepware configuration of CBM Zone 1 Tags | Lekshmi | 0% | 2024-07-22 | Completed
|  |  | Alert Mail feature of CBM | Subramani & Lekshmi + Mani ( HMCL) | 20% | 2024-07-27 | Yet to be validated
|  |  | CBM API for Instant and Overall Alarm Mail | Subramani | 0% | 2024-07-27 | API Development Completed
|  |  | SMTP Configuring for CBM | Subramani | 0% | 2024-07-27 | API Development Completed
Milestone | KPI | Demo | IIOT portal demo | TEAL+HMCL
|  |  | KPI demo - 3.3 & MIS | IIOT Team | 40% | 2024-08-20 | Demo initiated with Kamal ,Palanivel, Shivukumar,Sumant nagula , Mahesh babu,Vijay bhaskar,Bhavya,Vivek,Ganesh raj,Thirukumaran,Jaber i4metrics portal Credential shared for portal browsing Portal Training Demo - 27th Aug 2024
|  |  | KPI demo - 3.4 & MIS | IIOT Team | 40% | 2024-08-20 | Demo initiated with Kamal ,Palanivel, Shivukumar,Sumant nagula , Mahesh babu,Vijay bhaskar,Bhavya,Vivek,Ganesh raj,Thirukumaran,Jaber i4metrics portal Credential shared for portal browsing i4metrics portal Credential shared for portal browsing Portal Training Demo - 27th Aug 2024
|  |  | KPI demo - 2 & MIS | IIOT Team | 40% | 2024-08-20 | Demo initiated with Kamal ,Palanivel, Shivukumar,Sumant nagula , Mahesh babu,Vijay bhaskar,Bhavya,Vivek,Ganesh raj,Thirukumaran,Jaber i4metrics portal Credential shared for portal browsing Portal Training Demo - 27th Aug 2024
|  |  | Handover | IIOT Team | 100% | 2024-08-26 | Handover to Kamal ,Palanivel , Mani
Milestone | CBM | Demo | IIOT portal demo | TEAL+HMCL
|  |  | CBM demo for Zone 3.3 | IIOT Team | 100% | 2024-08-20 | Demo initiated with Palanivel, Bhavya
|  |  | CBM demo for Zone 3.4 | IIOT Team | 100% | 2024-08-20 | Demo initiated with Palanivel, Bhavya
|  |  | CBM demo for Zone 2 | IIOT Team | 100% | 2024-08-20 | Demo initiated with Palanivel, Bhavya
|  |  | CBM Demo for Zone 1 | IIOT Team | 100% | 2024-08-20 | Demo initiated with Palanivel, Bhavya
|  |  | Handover | IIOT Team | 100% | 2024-08-26 | Handover to Kamal ,Palanivel, Bhavya , Mani
Firewall Rule | Filewall Rule | Fire Wall Rule | Firewall Rule for Shop floor PC | IIOT & SCADA Team + Mani | 0% | 2024-07-19 | Completed and Mail sent to Mani
Milestone | Documentation | Documentation | Documentation and Traing
|  |  | OPC Server Failover- Documentation work | Documentation | 100% | 2024-08-06 | 1. Tranining Document 2. Manuals 3. Troubleshooting Document 4. Recovery Document
|  |  | IT Hardening - Documentation work | Documentation | 100% | 2024-08-06 | 1. IT Hardening HMCL Scope 2. PC recovery Document 3. Application Restore Document 3.1 Report EXE 3.2 SCADA Dashboard 3.3 KPI Dashboard 3.4 CBM Dashboard
|  |  | SOP Documents | Documentation | 40% | 2024-08-06 | 1. SCADA Client Application Manual 2. SCADA Client Application Training 3. Kepware Manual 4. API Manual 5. Web Jobs & Task Scheduler Manual 6. Database Creation and Configuration Manual 7. IIS Configuration Manual 8. KPI & CBM Client Application Manual 9. KPI & CBM Client Application Training

## Weekly Progress
Upcoming Major Milestones
SL.No | Activity | Task | Milestone End Date | Responsibility | Status | Remarks
1 | CBM Zone 1 Demo to customer | Entire portal was shown with live graphs | 2024-07-29 | Lekshmi | Completed | Kepware Zone tags Added. Portal Mapping in Progress. Scada and IIOT PC usage to be considerd
2 | Pending KPI Tags | Mail / Call to be set with PLC team for Rejection , Rework , Cycletime , Alarm , Variant Code for All Zones | 2024-08-02 | Vishnu | Mail Sent to PLC | Get Rework and Rejection Logic From Angu
3 | CBM Portal Validation | All Zones Portal Validation | 2024-08-08 | Lekshmi & Pavithra | Completed | At Site Validation -Commissioning
4 | CBM Portal Modification Points | Total 40 bugs raised | 2024-08-27 | Lekshmi | Inprogress
5 | 1.CycleTime for Partial station in zonewise 2.Rework for Zone2,3.3 3.Rejection Tag zone2,3.3 4.Updated Alarm address for Tags of all zones | 1.CycleTime for Partial station in zonewise 2.Rework for Zone2,3.3 3.Rejection Tag zone2, 4.Rejection Code and Description 3.3 5..Rejection Code and Description 3.4 5.Updated Alarm address for Tags of all zones 6.Updated Alarm address for Tags of all zones | 2024-09-03 | Veera | Yet to Start | Yet to receive Tag Addresses from PLC Programmer Only Zone 2 Rejection COde and Description recieved on 23rd Aug 24
6 | KPI Portal Validation | Zone 3.4 yet to be Implemented & validated | 2024-09-20 | Veera & Anne & Vishnu | Yet to Start
7 | CBM Instant and OverAll Alert , Alarm Mails Development | CBM Instant and OverAll Alert , Alarm Mails Development | 2024-07-27 | Subramani | Inprogress
8 | CBM Instant and OverAll Alert , Alarm Mails Validation | CBM Instant and OverAll Alert , Alarm Mails Validation | 2024-07-31 | Pavithra | Yet to Start
9 | MIS Report Generation with Bug fixes | Implementation of Zone Based MIS Report | 2024-08-13 | Santu | Completed | Given to Testing team for Final Testing
10 | CBM CBM Service to API Creation and Hosted in HMCL Portal | CBM CBM Service to API Creation | 2024-08-19 | Subramani & Vishnu | Completed | 3 Methods Response needs to be formatted
11 | MIS Report Validation | MIS Report Validation | 2024-08-03 | Testing Team | Completed and Bugs Raised
12 | ZoneDashboard | Implementation of ZoneDashboard | 2024-08-24 | Vishnu | Completed | Test run - 1 Bugs fixed and given to Testing team
13 | ZoneDashboard Validation |  |  | Anne | Test Run 1 - Completed
14 | Zonewise Dashboard Handover to customer | Zonewise Dashboard Handover to customer | 2024-08-31 | Vishnu | Yet to Start
15 | Zonewise Dashboard Final Demo to customer | Zonewise Dashboard Final Demo to customer | 2024-08-31 | Vishnu | Yet to Start
16 | Zone 3.4 Configuration in Gateways | Tag mapping fot Zone 3.4 | 2024-09-03 | Veera | Completed | Tags added in Kepware. Tag json to be implemented in Services
17 | Rejection Code and Description Configuration in Gateways | Tag mapping fot Zone 3.3 | 2024-08-31 | Veera | Yet to Start | Tags added in Kepware. Tag json to be implemented in Services
18 | Latest Alarm to be mapped in existing Zones | Latest Alarm to be mapped in existing Zones | 2024-08-05 | Veera | Yet to Start | Yet to receive Tag Addresses from PLC Programmer Prasanna
19 | CBM &KPI - High Memory Utilization 94% in DB | DB and Drive Memory Utilisation optimisation | Regular Monitoring | Santu/ Subramani | Continuous Process | Shrinking of DB to be done regularly to reduce the DB size and Log file sizes. Asked for Higher Specifications Server during Initial Project Discussion, will discuss with Kamal & Palani.
20 | OPC Server Failover- Documentation work | 1. Tranining Document 2. Manuals 3. Troubleshooting Document 4. Recovery Document | 2024-08-10 | Will be reviewed by internal team. | Yet to Start once Angu Confirms the Concept | Santhoshi / Kalai
21 | Firewall Rule for Shop floor PC | Co-ordinate with HMCL Manikandan | 2024-07-17 | Vishnupriya | Completed Followup to be done with Mani | Sheet updated and shared with Manikandan
22 | Random number generation of CBM TAG value | Set up Call with PC and Supplier | 2024-08-25 | Vishnu - Followup with PLC Team | InProgress
23 | except the random number generation for tags KPI-Demo to Customer | except the random number generation for tags KPI-Demo to Customer | 2024-08-27 | Vishnupriya | Completed
24 | except the random number generation for tags CBM Handover to customer | except the random number generation for tags CBM Handover to customer | 2024-08-27 | Lekshmi | Completed | CBM Portal Modifications - Inprogress
25 | except the random number generation for tags CBM Training to customer | except the random number generation for tags CBM Training to customer | 2024-08-27 | Lekshmi | InProgress | CBM Portal Modifications - Inprogress
26 | MIS Mail Recipients Added . | Mail to all Departments will be sent on 29th Aug 2024 | 2024-08-28 | Vishnupriya | Completed | Mail to all Departments will be sent on 29th Aug 2024
Documentation
16 | IT Hardening - Documentation work | 1. IT Hardening HMCL Scope 2. PC recovery Document 3. Application Restore Document 3.1 Report EXE 3.2 SCADA Dashboard 3.3 KPI Dashboard 3.4 CBM Dashboard | 2024-08-10 | Will be reviewed by internal team. | Yet to Start Once Angu Confirms | Santhoshi / Kalai
17 | SOP Documents | 1. SCADA Client Application Manual 2. SCADA Client Application Training 3. Kepware Manual 4. API Manual 5. Web Jobs & Task Scheduler Manual 6. Database Creation and Configuration Manual 7. IIS Configuration Manual 8. KPI & CBM Client Application Manual 9. KPI & CBM Client Application Training | 2024-08-10 | Will be reviewed by internal team. | 1. API Manual -Completed 2. Web Jobs & Task Scheduler Manual-Completed 3. Database Creation and Configuration Manual-Completed 4. IIS Configuration Manual-Completed 5. KPI & CBM Client Application Manual-Completed 6.Node js - Services pm2 Instructions - Completed | Santhoshi / Kalai

## HMCL_Tag_Status
KPI
| Zone | Tag provided | Tags mapped | Remarks | Target Date to recieve Tags
| Zone2 | 100% | 90% | Recieved all Tags Yet to Validate Rejection, Alarm , Rework , CycleTime , Variant Code | 8/2/2024 20-09-2024
| Zone3.3 | 100% | 90% | Recieved all Tags Yet to Validate Rejection, Alarm , Rework , CycleTime , Variant Code | 8/2/2024 20-09-2024
| Zone3.4 | 100% | 90% | Recieved all Tags Yet to Validate Rejection, Alarm , Rework , CycleTime , Variant Code | 8/2/2024 20-09-2024
CBM
| Zone | Tag provided | Tags mapped | Remarks
| Zone 1 | 100% | 80% | Live Tag Validation
| Zone2 | 100% | 80% | Live Tag Validation
| Zone 3 | 100% | 80% | Live Tag Validation
2024-07-06

## Stn_rev_1
PLC | Stations | Station Name | Zone | Machines_observed by IIOT | Cycle Time | Machine_Code | Machine type | Alarms Tags
| HBP1S2020A | Cell Holder Laser Marking Station-1 | Z2 | 1 | Operational Sequence - 17 Sec | M1 | Automatic | Recieved
| HBP1S2040A | Manual Cell Loading Station | Z2 | 2 | OK Sequence - 16 Sec NOK Sequence - 32 Sec | M2 | Manual | Recieved
| HBP1S2050A | Upper Cell Holder Loading Station | Z2 | 3 | Generaal - 37.5 Sec | M3 | Manual | Recieved
| HBP1S2050B | Upper Cell Holder Assembly Station 2 | Z2 | 4 |  | M4 | Manual | Recieved
| HBP1S2060A | Cell Stack Plasma Cleaning Station | Z2 | 5 | NOK Sequence - 55 Sec | M5 | Automatic | Recieved
| HBP1S2065A | Z Fixation Assembly Station | Z2 | 6 | Operational Sequence - 20 Sec | M6 | Semi Automatic | Recieved
| HBP1S2090A | Heat Stacking Station-1 | Z2 | 7 | Operational Sequence - NOK - 180 Sec | M7 | Semi Automatic | Recieved
| HBP1S2100A | Z-Fixation Plasma Cleaning Station | Z2 | 8 | Operational Sequence - NOK - 60 Sec | M8 | Semi Automatic | Recieved
| HBP1S2110A | Overhead Conveyor | Z2 | 9 | Operational Sequence - 67.17 | M9 |  | Recieved
PLC1 | HBP1S3020A | Resistance Welding Station-1 | Z3.3 | 1 | Operational Sequence - 437.75 Sec | M10
PLC1 | HBP1S3030A | Resistance Welding Station-2 | Z3.3 | 2 |  | M11
PLC1 | HBP1S3040A | Welding Integrity Checking Station-1 | Z3.3 | 3 | Operational Sequence - NOK - 115.0 Sec | M12
PLC1 | HBP1S3070A | Foam Dispensing Station | Z3.3 | 4 | Operational Sequence - NOK - 204.5 Sec | M13
PLC1 | HBP1S3075A | Monitor Clip & Z Fixation Spring Assembly Station | Z3.3 | 5 |  | M14
PLC1 | HBP1S3085A | Flipping Station | Z3.3 | 6 | Operational Sequence - OK - 48 Sec | M15
PLC1 | HBP1S3100A | Thermal Paste Dispensing Station | Z3.3 | 7 | Operational Sequence - OK - 234.0 Sec | M16
PLC1 | HBP1S3110A | BMS Assembly & Activation Station | Z3.3 | 8 | Operational Sequence - OK - 239.0 Sec | M17
PLC2 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station | Z3.3 | 9 | Operational Sequence - 188.22 | M18 |  | Recieved
PLC2 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station | Z3.3 | 10 | Operational Sequence - 235.5 Sec | M19 |  | Recieved
PLC2 | HBP1S3140A | Overhead Lifter & Lower Station | Z3.3 | 11 |  | M20 |  | Recieved
PLC2 | HBP1S3150A | Leak Testing & Plugging Station | Z3.3 | 12 | Operational Sequence - OK - 354.0 Sec | M21 |  | Recieved
| HBP1S4020A | Resistance Welding Station-1 | Z3.4 | 1 |  | M22
| HBP1S4030A | Resistance Welding Station-2 | Z3.4 | 2 |  | M23
| HBP1S4040A | Welding Integrity Checking Station-1 | Z3.4 | 3 |  | M24
| HBP1S4070A | Foam Dispensing Station | Z3.4 | 4 |  | M25
| HBP1S4075A | Monitor Clip & Z Fixation Spring Assembly Station | Z3.4 | 5 |  | M26
| HBP1S4085A | Flipping Station | Z3.4 | 6 |  | M27
| HBP1S4100A | Thermal Paste Dispensing Station | Z3.4 | 7 |  | M28
| HBP1S4110A | BMS Assembly & Activation Station | Z3.4 | 8 |  | M29
| HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station | Z3.4 | 9 |  | M30
| HBP1S4130A | End Cover Insertion & Glue Dispensing Station | Z3.4 | 10 |  | M31
| HBP1S4140A | Overhead Lifter & Lower Station | Z3.4 | 11 |  | M32
| HBP1S4150A | Leak Testing & Plugging Station | Z3.4 | 12 |  | M33
| Total Stations in Zone 2 , 3.3. & 3.4 |  |  | 33

## Stn_rev_2
| PLC | Stations | Station Name | Zone | Machines_observed by IIOT | Cycle Time | Machine_Code | Machine type | Alarms Tags
|  | HBP1S2020A | Cell Holder Laser Marking Station-1 | Z2 | 1 | Operational Sequence - 17 Sec | M1 | Automatic | Recieved
|  | HBP1S2040A | Manual Cell Loading Station | Z2 | 2 | OK Sequence - 16 Sec NOK Sequence - 32 Sec | M2 | Manual | Recieved
|  | HBP1S2050A | Upper Cell Holder Loading Station | Z2 | 3 | Generaal - 37.5 Sec | M3 | Manual | Recieved
|  | HBP1S2050B | Upper Cell Holder Assembly Station 2 | Z2 | 4 |  | M4 | Manual | Recieved
|  | HBP1S2060A | Cell Stack Plasma Cleaning Station | Z2 | 5 | NOK Sequence - 55 Sec | M5 | Automatic | Recieved
|  | HBP1S2065A | Z Fixation Assembly Station | Z2 | 6 | Operational Sequence - 20 Sec | M6 | Semi Automatic | Recieved
|  | HBP1S2090A | Heat Stacking Station-1 | Z2 | 7 | Operational Sequence - NOK - 180 Sec | M7 | Semi Automatic | Recieved
|  | HBP1S2100A | Z-Fixation Plasma Cleaning Station | Z2 | 8 | Operational Sequence - NOK - 60 Sec | M8 | Semi Automatic | Recieved
|  | HBP1S2110A | Overhead Conveyor | Z2 | 9 | Operational Sequence - 67.17 | M9 |  | Recieved
| PLC1 | HBP1S3020A | Resistance Welding Station-1 | Z3.3 | 1 | Operational Sequence - 437.75 Sec | M10
| PLC1 | HBP1S3030A | Resistance Welding Station-2 | Z3.3 | 2 |  | M11
172.18.40.43 | PLC1 | HBP1S3040A | Welding Integrity Checking Station-1 | Z3.3 | 3 | Operational Sequence - NOK - 115.0 Sec | M12
|  | HBP1S3050A | Welding Integrity Checking Station-2 | Z3.3 | 3 | Operational Sequence - NOK - 115.0 Sec | M13
| PLC1 | HBP1S3070A | Foam Dispensing Station | Z3.3 | 4 | Operational Sequence - NOK - 204.5 Sec | M14
| PLC1 | HBP1S3085A | Flipping Station | Z3.3 | 6 | Operational Sequence - OK - 48 Sec | M15
| PLC1 | HBP1S3100A | Thermal Paste Dispensing Station | Z3.3 | 7 | Operational Sequence - OK - 234.0 Sec | M16
| PLC1 | HBP1S3110A | BMS Assembly & Activation Station | Z3.3 | 8 | Operational Sequence - OK - 239.0 Sec | M17
| PLC2 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station | Z3.3 | 9 | Operational Sequence - 188.22 | M18 |  | Recieved
| PLC2 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station | Z3.3 | 10 | Operational Sequence - 235.5 Sec | M19 |  | Recieved
| PLC2 | HBP1S3140A | End Cover Insertion & Glue Dispensing Station | Z3.3 | 11 | Operational Sequence - 235.5 Sec | M20
| PLC2 | HBP1S3150A | Leak Testing & Plugging Station | Z3.3 | 12 | Operational Sequence - OK - 354.0 Sec | M21 |  | Recieved
| PLC1 | HBP1S4020A | Resistance Welding Station-1 | Z3.4 | 1 | Operational Sequence - 437.75 Sec | M22
| PLC1 | HBP1S4030A | Resistance Welding Station-2 | Z3.4 | 2 |  | M23
| PLC1 | HBP1S4040A | Welding Integrity Checking Station-1 | Z3.4 | 3 | Operational Sequence - NOK - 115.0 Sec | M24
|  | HBP1S4050A | Welding Integrity Checking Station-2 | Z3.4 | 3 | Operational Sequence - NOK - 115.0 Sec | M25
| PLC1 | HBP1S4070A | Foam Dispensing Station | Z3.4 | 4 | Operational Sequence - NOK - 204.5 Sec | M26
| PLC1 | HBP1S4085A | Flipping Station | Z3.4 | 6 | Operational Sequence - OK - 48 Sec | M27
| PLC1 | HBP1S4100A | Thermal Paste Dispensing Station | Z3.4 | 7 | Operational Sequence - OK - 234.0 Sec | M28
| PLC1 | HBP1S4110A | BMS Assembly & Activation Station | Z3.4 | 8 | Operational Sequence - OK - 239.0 Sec | M29
| PLC2 | HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station | Z3.4 | 9 | Operational Sequence - 188.22 | M30 |  | Recieved
| PLC2 | HBP1S4130A | End Cover Insertion & Glue Dispensing Station | Z3.4 | 10 | Operational Sequence - 235.5 Sec | M31 |  | Recieved
| PLC2 | HBP1S4140A | End Cover Insertion & Glue Dispensing Station | Z3.4 | 11 | Operational Sequence - 235.5 Sec | M32
| PLC2 | HBP1S4150A | Leak Testing & Plugging Station | Z3.4 | 12 | Operational Sequence - OK - 354.0 Sec | M33 |  | Recieved
|  | Total Stations in Zone 2 , 3.3. & 3.4 |  |  | 33

## StationList_Rev3_Final
29-05-24
| PLC | Stations | Station Name | Zone | Machines_observed by IIOT | Cycle Time as per DAP | SCADA CT Observation | Machine_Code | Machine type | Alarms Tags
|  | HBP1S2020A | Cell Holder Laser Marking Station-1 | Z2 | 1 | Operational Sequence - 17 Sec | 16.5 | M1 | Automatic | Recieved
|  | HBP1S2040A | Manual Cell Loading Station |  | 3 | OK Sequence - 16 Sec NOK Sequence - 32 Sec | 15.5 | M2 | Manual | Recieved
|  | HBP1S2045A | module pressing station 1 |  | 4 |  | 73.5 | M3
|  | HBP1S2045B | module pressing station 2 |  | 5 |  | 36 | M4
|  | HBP1S2050A | Upper Cell Holder Loading Station |  | 6 | Generaal - 37.5 Sec | 58 | M5 | Manual | Recieved
|  | HBP1S2050B | Upper Cell Holder Assembly Station 2 |  | 7 |  | 50 | M6 | Manual | Recieved
|  | HBP1S2060A | Cell Stack Plasma Cleaning Station |  | 8 | NOK Sequence - 55 Sec | 54.5 | M7 | Automatic | Recieved
|  | HBP1S2065A | Z Fixation Assembly Station |  | 9 | Operational Sequence - 20 Sec | 19.5 | M8 | Semi Automatic | Recieved
|  | HBP1S2090A | Heat Stacking Station-1 |  | 10 | Operational Sequence - NOK - 180 Sec | 185 | M9 | Semi Automatic | Recieved
|  | HBP1S2100A | Z-Fixation Plasma Cleaning Station |  | 11 | Operational Sequence - NOK - 60 Sec | 60 | M10 | Semi Automatic | Recieved
| PLC1 | HBP1S3020A | `+ve Resistance Welding Station -1 | Z3.3 | 1 | Operational Sequence - 437.75 Sec | 427.75 | M11
| PLC1 | HBP1S3020B | `-ve Resistance Welding Station -1 |  | 2 | Operational Sequence - 437.75 Sec | 427.75 | M12
| PLC1 | HBP1S3030A | `+ve Resistance Welding Station -2 |  | 3 |  | 427.75 | M13
| PLC1 | HBP1S3030B | `-ve Resistance Welding Station -2 |  | 4 |  | 427.75 | M14
172.18.40.43 | PLC1 | HBP1S3040A | Welding Integrity Checking Station-1 |  | 5 | Operational Sequence - NOK - 115.0 Sec | 167 | M15
|  | HBP1S3050A | Welding Integrity Checking Station-2 |  | 6 | Operational Sequence - NOK - 115.0 Sec | 217.5 | M16
| PLC1 | HBP1S3070A | Foam Dispensing Station |  | 7 | Operational Sequence - NOK - 204.5 Sec | 204.5 | M17
| PLC1 | HBP1S3085A | Flipping Station |  | 8 | Operational Sequence - OK - 48 Sec |  | M18
| PLC1 | HBP1S3100A | Thermal Paste Dispensing Station |  | 9 | Operational Sequence - OK - 234.0 Sec | 234 | M19
| PLC1 | HBP1S3110A | BMS Assembly & Activation Station |  | 10 | Operational Sequence - OK - 239.0 Sec | 239 | M20
| PLC2 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station |  | 11 | Operational Sequence - 188.22 |  | M21 |  | Recieved
| PLC2 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station |  | 12 | Operational Sequence - 235.5 Sec |  | M22 |  | Recieved
| PLC2 | HBP1S3140A | End Cover Insertion & Glue Dispensing Station |  | 13 | Operational Sequence - 235.5 Sec |  | M23
| PLC2 | HBP1S3150A | Leak Testing & Plugging Station |  | 14 | Operational Sequence - OK - 354.0 Sec | 183 | M24 |  | Recieved
| PLC1 | HBP1S4020A | `+ve Resistance Welding Station -1 | Z3.4 | 1 | Operational Sequence - 437.75 Sec |  | M25
| PLC1 | HBP1S4020B | `-ve Resistance Welding Station -1 |  | 2 |  |  | M26
| PLC1 | HBP1S4030A | `+ve Resistance Welding Station -2 |  | 3 | Operational Sequence - NOK - 115.0 Sec |  | M27
|  | HBP1S4030B | `-ve Resistance Welding Station -2 |  | 4 | Operational Sequence - NOK - 115.0 Sec |  | M28
| PLC1 | HBP1S4040A | Welding Integrity Checking Station-1 |  | 5 | Operational Sequence - NOK - 204.5 Sec |  | M29
| PLC1 | HBP1S4050A | Welding Integrity Checking Station-2 |  | 6 | Operational Sequence - OK - 48 Sec |  | M30
| PLC1 | HBP1S4070A | Foam Dispensing Station |  | 7 | Operational Sequence - OK - 234.0 Sec |  | M31
| PLC1 | HBP1S4085A | Flipping Station |  | 8 | Operational Sequence - OK - 239.0 Sec |  | M32
| PLC2 | HBP1S4100A | Thermal Paste Dispensing Station |  | 9 | Operational Sequence - 188.22 |  | M33 |  | Recieved
| PLC2 | HBP1S4110A | BMS Assembly & Activation Station |  | 10 | Operational Sequence - 235.5 Sec |  | M34 |  | Recieved
| PLC2 | HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station |  | 11 | Operational Sequence - 235.5 Sec |  | M35
| PLC2 | HBP1S4130A | End Cover Insertion & Glue Dispensing Station |  | 12 | Operational Sequence - OK - 354.0 Sec |  | M36 |  | Recieved
|  | HBP1S4140A | End Cover Insertion & Glue Dispensing Station |  | 13 | Operational Sequence - OK - 354.0 Sec |  | M37
|  | HBP1S4150A | Leak Testing & Plugging Station |  | 14 | Operational Sequence - OK - 354.0 Sec |  | M38
| Total Stations in Zone 2 , 3.3. & 3.4 |  |  |  | 39

## AssetTable_Final
AssetID | FunctionName | AssetName | AssetDescription | EOL | CompanyCode | PlantCode | ewonnumber | Zones
M1 | HMBT01 | OP2020A | Cell Holder Laser Marking Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M2 | HMBT01 | OP2040A | Cell Stack Plasma Cleaning Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M3 | HMBT01 | OP2045A | Pressing Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M4 | HMBT01 | OP2045B | Pressing Station-2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M5 | HMBT01 | OP2050A | Upper Cell Holder Loading Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M6 | HMBT01 | OP2050B | Upper Cell Holder Loading Station-2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M7 | HMBT01 | OP2060A | Cell Stack Plasma Cleaning Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M8 | HMBT01 | OP2065A | Z Fixation Assembly Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M9 | HMBT01 | OP2090A | Heat Stacking Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M10 | HMBT01 | OP2100A | Z Fixation Plasma Cleaning Station | 1 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 2
M11 | HMBT01 | OP3020A | Positive Resistance Welding Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M12 | HMBT01 | OP3020B | Negative Resistance Welding Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M13 | HMBT01 | OP3030A | Positive Resistance Welding Station-2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M14 | HMBT01 | OP3030B | Negative Resistance Welding Station-2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M15 | HMBT01 | OP3040A | Welding Integrity Checking Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M16 | HMBT01 | OP3050A | Welding Integrity Checking Station-2 | 1 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M17 | HMBT01 | OP3070A | Foam Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M18 | HMBT01 | OP3085A | Flipping Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M19 | HMBT01 | OP3100A | Thermal Paste Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M20 | HMBT01 | OP3110A | BMS Assembly & Activation Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M21 | HMBT01 | OP3120A | Plasma Cleaning & Cell Module Insertion Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M22 | HMBT01 | OP3130A | End Cover Insertion & Glue Dispensing Station - 1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M23 | HMBT01 | OP3140A | End Cover Insertion & Glue Dispensing Station - 2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M24 | HMBT01 | OP3150A | Leak Testing & Plugging Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.3
M25 | HMBT01 | OP4020A | Positive Resistance Welding Station -1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M26 | HMBT01 | OP4020B | Negative Resistance Welding Station -1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M27 | HMBT01 | OP4030A | Positive Resistance Welding Station -2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M28 | HMBT01 | OP4030B | Negative Resistance Welding Station -2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M29 | HMBT01 | OP4040A | Welding Integrity Checking Station-1 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M30 | HMBT01 | OP4050A | Welding Integrity Checking Station-2 | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M31 | HMBT01 | OP4070A | Foam Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M32 | HMBT01 | OP4085A | Flipping Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M33 | HMBT01 | OP4100A | Thermal Paste Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M34 | HMBT01 | OP4110A | BMS Assembly & Activation Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M35 | HMBT01 | OP4120A | Plasma Cleaning & Cell Module Insertion Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M36 | HMBT01 | OP4130A | End Cover Insertion & Glue Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M37 | HMBT01 | OP4140A | End Cover Insertion & Glue Dispensing Station | 0 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4
M38 | HMBT01 | OP4150A | Leak Testing & Plugging Station | 1 | TL_HBT | TL_HBT01 | TEAL_Demo_DLK | Zone 3.4

## CBM TAGS_for june3 run
Zone 3.3 | main panel energy meter -1 | units_consumed_in_kwh
r phasevoltage
y phasevoltage
b phasevoltage
running_load_in_kw
r phaseCurrent
y phaseCurrent
b phaseCurrent
frequency
power
| main panel energy meter -1 | units_consumed_in_kwh
r phasevoltage
y phasevoltage
b phasevoltage
running_load_in_kw
r phaseCurrent
y phaseCurrent
b phaseCurrent
frequency
power
| Lifecycle | AirFlow
| Lifecycle | AirPressure
| Overhead lifter Conveyor near OP 3140 | drive_temperature
| Overhead lifter Conveyor near OP 3140 | motor_running_torque
| Overhead lifter Conveyor near OP 3140 | motor_temperature
| Overhead lifter Conveyor near OP 3140 | r phasecurrent
| Overhead lifter Conveyor near OP 3140 | b phasecurrent
| Overhead lifter Conveyor near OP 3140 | y phasecurrent
| Drive motor for recirculation 3160A | drive_temperature
| Drive motor for recirculation 3160A | motor_running_torque
| Drive motor for recirculation 3160A | motor_temperature
| Drive motor for recirculation 3160A | r phasecurrent
| Drive motor for recirculation 3160A | b phasecurrent
| Drive motor for recirculation 3160A | y phasecurrent

## Machine_flow
Date | S.no | Observations
22/05/2024 | 1 | op20 & op30 same operation
| 2 | 20a - positive welding 119 points
| 3 | 20b - negative welding 47 points
| 4 | 130 & 140 same station , same operation but consider as different station because individual parts running
| 5 | 150 leak test
| 6 | op20 both welding completed, then 40 & 50 welding integrity , then poitns will check in op60(manual checking), if not welded properly no nok parts, parts will move to op20 for rework
| 7 | Combining 20a+20b for cycletime - plc side need to taken(informed with prasanna)

## HMCL Portal Issues
SL.No | Issue | Development / Modification Status | Date of Completion | Testing Status | Remarks | S.No | Module | Defect | Dev Status
1 | Alarm + Icon not showing | Completed |  |  | Occured again during Demo , same fontawesome issue publish time issue | 1 | Login | Refresh icon not displaying | Completed Available in Application VM
2 | Data not displayed after expanding | Occured once , need to monitor |  |  |  | 2 | Login | Icon near sign in not displaying | Completed Available in Application VM
3 | No data available is not showing in shiftwise production summary -daywise production | Completed |  |  |  | 3 | Login | Username icon not displaying | Completed Available in Application VM
4 | Cycle time live - no data available message is also not showing,and shift is showing s2 | Completed |  |  |  | 4 | Login | Sign in icon not displaying | Completed Available in Application VM
5 | Batch wise Hourly OEE showing 0 at top | SIM Code - Yet to Start |  |  | SIM Code will be integrated for this fix. | 5 | Login | Clicking on teal logo should refresh the page but 403 - forbidden error is displaying(Mapped URL does not have "/frontend" on click) | Completed Available in Application VM
6 | Latest machine event-its not even showing any message | Losses for Machine is not yet configured , will get data once it is done. |  |  |  | 6 | Forgot password | mail not sent when clicked but password got changed | Reason Given
7 | Last update shift in Footer showing Shift not showing proper data , sometimes showing NA | Inprogress |  |  |  | 7 | Forgot password | Forgot password icon not displaying | Completed Available in Application VM
8 | Machine Status Live not showing in KPI popup | Completed |  |  |  | 8 | Change password | mail not sent when clicked but password got changed | Reason Given
9 | Logout page not redirecting to Login Page | Completed | 20/05/2024 |  |  | 9 | Main Dashboard | Zone 3 machine name displaying out of machine status bar box | Removed Z3.3 for adjusting to width of bar "Completed Available in Application VM"
10 | Fontawsome images not loading in Login Page | Completed |  |  |  | 10 | Main Dashboard | Hourly pop-up - If value is 0 then graph should not display(Displaying bar with 0 on top) | Locally Done
11 | Latest Captcha code Moved to HMCL | Completed | 21/05/2024 |  | Removed 0 and O from listing in Captcha for user experience | 11 | MTTR | Alarm description is getting hidden in X-axis
12 | CT Historic Movement dropdown - Not required as compulsory field | Completed - as removed madatory conditions for this field |  |  | need to remove dropdown ?? ( Discuss internally ) | 12 | CT Live | Loading icon not displaying till data displays | Completed Available in Application VM
13 | Test_119 Webjob Issue for Data posting of Zone 3.3 Stations | Completed |  |  |  | 13 | CT Live | Data not displaying
14 | Cycle TIme Historic WebJob Isue for Data Posting | Completed |  |  |  | 14 | CT Live | No data message not displaying if no data is there to display | Locally Done
15 | Renamed Plant Name - to Tirupati Plant | Completed |  |  |  | 15 | CT Live | Don't display CT if 0.00 or if part number is 0
16 | Chronological order for dates and historic View | Completed |  |  |  | 16 | Main Dashboard | When hovered on carousal then carousal should not move(But it is moving) | Completed Available in Application VM
17 | Clicking on teal logo should refresh the page but 403 - forbidden error is displaying(Mapped URL does not have "/frontend" on click) | Completed - Locally on 30-05-2024 Available in Application Server |  |  |  | 17 | Alarm Live | Machine status displying as undefined sometimes (in Alert rawtable - Gateway issue)
18 | Portal Settings related Modifications and changes will be moved to HMCL by Wednesday ( 5th June 2024 ) |  |  |  |  | 18 | Latest machine events | Autorunning displaying as No Autorunning (Last occurrence) even if Auto running was there
19 | User ROle management Implementation in HMCL | User , User groups added in Menu |  |  |  | 19 | Latest machine events | Shift displaying as N/A in footer | Locally Done
20 | Refresh icon not displaying. Icon near sign in not displaying. Username icon not displaying. Sign in icon not displaying. | Duplicate Issue refer point 10 Completed |  |  |  | 20 | Common | Sort machine w.r.t machine code in all Machine selection dropdowns | Completed Available in Application VM
21 | mail not sent when clicked but password got changed. | Explanation Given |  |  |  | 21 | Menu | Enable all required settings like Role, Users, etc in menu | Completed Available in Application VM
22 | mail not sent when clicked but password got changed. | Explanation Given |  |  |  | 22 | Downtime reason pareto | Alarm description displaying out of tooltip
23 | Forgot password icon not displaying. | Same Issue as Point 10 |  |  |  | 23 | Main Dashboard | KPI pop-up - If value is 0 then graph should not display(Displaying bar with 0 on top) | Locally Done
24 | Main Dashboard - When hovered on carousal then carousal should not move(But it is moving) | Completed |  |  |  | 24 | Main Dashboard | Machine status timeline bar not displaying in KPI pop-up | Completed Available in Application VM
25 | Alarm Live - Machine status displaying as undefined sometimes (in Alert rawtable - Gateway issue) |  |  |  |  | 25 | Main Dashboard | KPI pop-up data not displaying | Completed Available in Application VM
26 | Latest machine events - Autorunning displaying as No Autorunning (Last occurrence) even if Auto running was there? |  |  |  |  | 26 | Main Dashboard | After opening pop-up data is not refreshing after 2 minutes | On Hold
27 | Latest machine events - Shift displaying as N/A in footer. | Duplicate Issue refer point 7 Completed
28 | Common - Sort machine w.r.t machine code in all Machine selection dropdowns
29 | Menu - Enable all required settings like Role, Users, etc in menu. | Duplicate Issue refer point 19 User , User groups added in Menu
30 | Main Dashboard - Zone 3 machine name displaying out of machine status bar box. | Completed , removed Z3.3
31 | Main Dashboard - Hourly pop-up - If value is 0 then graph should not display(Displaying bar with 0 on top) | Modified yet to test
32 | MTTR - Alarm description is getting hidden in X-axis.
33 | CT Live - Loading icon not displaying till data displays. | Working in local
34 | CT Live - Data not displaying.
35 | CT Live - No data message not displaying if no data is there to display. | Duplicate Issue refer point 4 Completed
36 | CT Live - Don't display CT if 0.00 or if part number is 0.

## MIS_Bug List
SL.No | MIS Issue List | Responsibility | Target Date | Dev Status | Testing Status | Milestone
1 | Zone 2 summary - Utilization, OEE displaying wrong data | Santu | 2024-06-27 | Completed | Yet to Test | 2024-06-02
2 | Zone 2 summary graph alignment on stack graph is not proper | Santu | 2024-06-27 | Yet to Start(Not required as per testing team ) | Yet to Test | 2024-06-02
3 | Zone 2 summary table below graph has station overlap in the table | Santu | 2024-06-27 | Completed | Working fine | 2024-06-02
4 | Zone 2 summary Give correct tooltip or disable tooltip | Santu | 2024-06-27 | Completed (have to disscuss with testing team)(27-06-2024) | Yet to Test | 2024-06-02
5 | Partwise CT - Changeover time for 4 to 5 is there but not there for 3 - 4 | Santu | 2024-06-27 | Actual cyc time is zero that's why its not coming | Clarity - Should it display part to part with 0 Actual time or should it be ignored | 2024-07-02
6 | Part wise CT - Border for header | Santu | 2024-06-27 | Completed | Working fine | 2024-07-02
7 | Partwise CT - Mention units for Actual CT and Part to part CT | Santu | 2024-06-27 | Completed | Actual Cycletime is displaying in Secs not in HH:MM:SS format(Change the unit for actual CT) | 2024-07-02
8 | Partwise CT - Clarity on the column Reasons | Santu | 2024-06-27 | Completed | Working fine | 2024-07-02
9 | Occurrence value is wrong and Occurrence spelling is also wrong | Santu | 2024-06-28 | Reopen | Working fine | 2024-07-02
10 | Both Duration and Occurrence value in zone 2 and 3.3 value is wrong | Santu | 2024-06-28 | Reopen | Working fine | 2024-07-02
11 | Index - Hourly tracker zone 1 link in index is going to Hourly tracker zone 2 page | Santu | 2024-06-28 | Reopen | Working fine | 2024-07-02
12 | Index - Cycle time zone 1 link in index is going to Cycle time zone 2 page | Santu | 2024-06-28 | Reopen | Working fine | 2024-07-02
13 | Cycletime zone 3.4 - Data not available text displaying in wrong place | Santu | 29-06-2024 | Reopen | Working fine | 2024-07-02
14 | Cycletime zone 2 page header displaying as Zone 3.4 | Santu | 29-06-2024 | Completed (have to disscuss with testing team)(27-06-2024) | Working fine | 2024-07-02
15 | Cycletime zone 2 displaying no. of variants ran : 1 but no data displaying | Santu | 29-06-2024 | Completed(27-06-2024) | Working fine | 2024-07-02
16 | Hourly tracker(All zones) - APQ OEE restriction to 100% | Santu | 29-06-2024 | Completed | Completed | 2024-07-02
17 | Zone 2 summary - Utilization - Losstime difference of more than 200 mins between Manual calculation and displayed value | Santu | 2024-07-01 | Completed | Working fine | 2024-07-02
18 | Production date is not logging as 8:00:00 to 8:00:00 | Veera | 2024-07-01 | Yet to Start | Yet to Test | 2024-07-02
19 | Cycle Time logged in DB but not binding in MIS Zone Summary Sheet | Santu | 2024-07-01 | Completed | Yet to Test | 2024-07-02
20 | Zone 3.3 summary - Utilization difference of more than 200 mins between Manual calculation and displayed value | Santu |  | Completed | Working fine | 2024-07-02
21 | Hourly tracker(All zones) - Check correctness of graph displaying in bottom | Santu |  | Completed | Yet to Test
22 | Mail body - End time should be for whole day(displaying shift 1 end time) | Santu |  | Completed | Working fine
23 | PLant name , Line name in mail Body | Santu | 18/07/2024 | Completed | Working fine
24 | Excel sheet name should also have line Name | Santu | 18/07/2024 | Completed | Working fine
25 | Zone 2 summary - Availability displaying wrong value | Santu | 18/07/2024 | Completed | Working fine
26 | X axis Y axis label is not there |  |  | Yet to Start
27 | Change OK colour to green and NOK colour to red |  |  | Yet to Start
28 | Hide this table in hourly tracker |  |  | Yet to Start
29 | APQ OEE % to be added in Production summary pages |  |  | Yet to Start

## CBM Portal Issues
SL.No | Validated open points | priority level | Traget date | Revised date | Dev Status | Testing Status | Remarks
1 | Summary dashboard-Total Sensor 276-Connected 0-Disconnected 1,Alarm 1 showing ,but in some scenario disconnected 0 is showing alarm 0 is showing - kindly check in frontend,Kepware side its showing status is good | High | 8/14/2024 | 2024-08-26 | Completed in Locally |  | logic need to check Table Name to be identified SP to be found
2 | change in sensor name /alignment change | Medium | 8/16/2024 | 2024-08-24 | Completed in Locally |  | either the length should reduce or alignment need to change in the summary page
3 | Overview page overlap of graph words | Low |  |  | Completed
4 | Number alignment of total alarms generated this months is not proper | Low | 8/16/2024 | 2024-08-24 | Completed in Locally
5 | Alert summary page alignment of tab is not proper | Medium | 8/16/2024 | 2024-08-24 | Completed in Locally |  | Need to change the code format
6 | In today table the end time and duration is not showing , but in yesterday its showing | Low | 8/16/2024 | 2024-08-27 | Yet to Start |  | need clarity,end time and duration for today table.
8 | In Alert summary custom change of from and to date format | Medium | ~ | ~ | Not an Issue |  | We are following TVS implementation in HMCL also.
9 | In Historic Tabular view change of from and to date format | Medium | ~ | ~ | Not an Issue |  | We are following TVS implementation in HMCL also.
10 | Alarm summary from and to date selection for two days , but getting selected for all days logic clarification | Low | ~ | ~ | Not an Issue |  | Only in Historic 2 days data we are restricting due to volumn of data. Alert - we'll show based on custom date selected
11 | In Historic tabular view no message popup for when station not get selected without selecting giving view | Low | 8/20/2024 | 2024-08-24 | Completed in Locally |  | Completed in Locally
12 | Only 5 station can be selected message is not coming in historic page , but after the selection of 5 station other stations disabled | Medium | 8/20/2024 | 2024-08-24 | Completed in Locally |  | Completed in Locally
13 | after selection of 1 or 5 station its taking more time to load the value | Low | 2024-10-08 | 2024-08-24 | Completed
14 | in select station option not available coming | Low | 2024-10-08 | ~ | Completed |  | Working FIne
15 | moving from dashboard and historic page to setting page it showing back image , again once we refresh the page is coming | High | 8/13/2024 | 2024-08-26 | InProgress |  | Need support
16 | sensor limit configuration table alignment need to be checked | Medium | 8/16/2024 | 2024-08-26 | Not an Issue
17 | Tag address in add sensor "Tag address should right format message to be given" | Low | 8/20/2024 | 2024-08-26 | Completed in Locally
18 | In Tag address what ever correct format we give also its not accepting change in format required | Low | 8/16/2024 | 2024-08-24 | Completed in Locally |  | Completed in Locally
19 | In edit threshold the design lsl and hsl value after editing its getting swap lsl in hsl and vice versa | High | 8/13/2024 | ~ | Completed
20 | in sensor type list the alignment of the table is not correct in edit column design hsl value is showing | Medium | 8/16/2024 | 2024-08-26 | Completed in Locally |  | Completed in Locally
21 | In sensor type list ,in add sensor type unbale to scroll down , both the scroll button move the back page | Low | 8/13/2024 | 2024-08-23 | Completed
22 | Error message display second to be added | Low | 2024-10-08 | 2024-08-24 | Completed in Locally |  | Completed in Locally
23 | in all add type after closed and open again the edit value are there no new tab is not coming | Low |  | 2024-08-24 | InProgress |  | Completed locally for unit,catgeory,device,add sensor type ,add station,code format need to change
24 | sensor type which we are adding newly should get display in 1 line or top of the list , but its showing at last in list, even no search option to search | Medium | 8/13/2024 | 2024-08-27 | Completed in Locally
25 | In Station list after editing without give save the value is get saved in tab | Low |  | 2024-08-27 | Clarity from Pavithra
26 | In Station list after editing if we give cancel the typed valued get save in that tab | Low | 8/16/2024 | ~ | Completed |  | Working FIne
27 | In device list duplicate of device name is getting added | High | 8/16/2024 | 2024-08-24 | Completed in Locally
28 | In device type list ,in add sensor type unbale to scroll down , both the scroll button move the back page | Low | 8/16/2024 | ~ | Completed |  | Working FIne
29 | Error message display second to be added | Low | 8/13/2024 | 2024-08-24 | Completed in Locally |  | Completed in Locally
30 | In device list when edit option got selected after closing and opening still it showing in edit state | Medium | 8/16/2024 | 2024-08-27 | Not an Issue
31 | In category list when edit option got selected after closing and opening still it showing in edit state | Medium |  | 2024-08-27 | Not an Issue
32 | In category list duplicate of device name is getting added | Medium | 8/16/2024 | 2024-08-24 | Completed in Locally
33 | In category list ,in add sensor type unbale to scroll down , both the scroll button move the back page | Low | 8/16/2024 | ~ | Completed |  | Working FIne
34 | Error message display second to be added | Low | 8/13/2024 | 2024-08-24 | Completed in Locally |  | Completed in Locally
35 | In Unit list when trying to add new unit its showing message like unit null type already exist | High | 8/13/2024 | ~ | Completed
36 | In unit list when trying to delete the existing data its showing message like something went wrong | High | 8/13/2024 | ~ | Completed
37 | In unit list when tried to edit and when give save its showing successful message , but the value is not getting saved | High | 8/13/2024 | ~ | Completed
38 | In dashboard in actual ,big value and minus value we are getting | High | 8/13/2024 | 2024-08-26 | Completed
39 | CBM Summarry - Cards grouping based on Parameter, remove Station names to avoid individual cards | High | ~ | 2024-08-27 | InProgress |  | Most of the sensors are grouped ,but need clarity for grouping the sensors after validation. for CBM.
40 | Add Sensor > On selecting Sensor Type , Unit is getting binded in Tag Address input | Medium | ~ | 2024-08-26 | Completed in Locally |  | Completed in Locally
| AddEmail>On adding email id its getting added ,when trying to delete and cancelling the delete option by giving keep it option the add email option is getting closed immediately and all email id added is not getting displayed after opeing the email setting again | High | 2024-05-09 | 2024-06-09 | Completed
| Add Email> After ading mail id if you close the email setting and opening it agian the mail ids added is not there, it showing nothing | High | 2024-05-09 | 2024-06-09 | Completed
| Overall Alarm >when the export csv file >Custom date > file getting downloaded > but in file we have only 3 entries [03-09-2024] | High | 2024-05-09 | 2024-06-09 | Completed
| Issue List | Count | Completed | Inprogress | Yet to Start | Not an Issue | Clarity required
| High | 12 | 7- Deployed 1-Locally completed | 4 | 0 | 0 | 0
| Medium | 12 | 4-Locally completed | 2 | 1 | 5 | 0
| Low | 18 | 7-Deployed 7-Locally completed | 1 | 1 | 1 | 1

## Zone Dashboard issues
S.No | Module | Defect | Dev Status | Testing Status
1 | HMI station details | Old data is displaying - Should display today's data | Updated with current Date instead of Time_Stamp Desc & with buffer of 2 mins in threshold - Completed | Working fine
2 | HMI station details | If data not there for current data displaying '-' instead of empty box or 0 | Completed | Working fine
3 | Hourly pop-up | If data not there for current data display No data Available | By default Target Graphs will be plotted since we do Target caluclation using Machine CT | Working fine
4 | All station OEE | If data not there for current data display No data Available | Completed | Working fine
5 | All station utilization | If data not there for current data display No data Available | Completed | Working fine
6 | All station cycletime | If data not there for current data display No data Available | Completed | Working fine
7 | HMI station details | On click of station box loading symbol should display in the centre of the HMI station details box | Checked working fine in one 3.3 as well. | Issue persist for zone 3.3
8 | HMI station details | On click of Shift tab should load the station details - currently loading if previous opened HMI station details tab is closed | Completed | Working fine
9 | Hourly pop-up | X-axis and y-axis lables missing | Completed
10 | HMI station details | When hovered on pie chart the sides are getting hidden | Removed Animation on Pie Chart Completed
11 | HMI station details | Utilization if 0 displaying as NaN | Completed
12 | HMI station details | If No data then display '-' or else display value | Completed
13 | HMI station details | OK-123 and NOK - 0 is there but displaying '-' in portal for both OK and NOK | Working fine

## Lesson learnt
27/05/2024
Problem:
1 | VS code should install w.r.t system setup not user setup If user setup get reason from customer IT team |  | Solution: | Move node files from adminsitrator folder to user,defalutpool so that it will execute in command prompt
yet to check for vs code (other alternative)
If you choose to opt for user setup, you do not need to provide any administrator privileges. On the other hand, if you choose to go with the system setup, you must use administrator permission.
user setup option installs the app in the Local AppData folder, whereas the system setup option uses the Program Files folder to be installed on your computer.
You can find VS Code only in the current user account if you choose the user setup. However, if you choose the system setup, you can find the app in all the user accounts.
You cannot find the Check for Updates option in the Help menu of user setup.
30/05/2024
Problem: | Due to HMCL netwrok traffic first time tag loading when plc service started, its taking more time to load all tag(observed after configuring 800tags) | Solution: | Approached Mani - yet to troubleshoot(31/05/2024)
Observation: Morning apprx 1 min la all 800 tags loaded, but later 1 min la 2 stn tag-(64) only loading in plc service
30/05/2024
Problem: | 0 value entered in raw table during gateway service restart | Solution: | Json tag order format changed (ok,nok,,total,rework,variant) and checked multiple times by manualy restarted and no 0 value posted
Note: Due to this for 3 to 5 sec tag posting to Manual mode, auto mode, auto running will be 0 --->machine status will 3
Need to check for variant, if variant 0 posted(V0), already sp handled no data inserted if v0 is posted
30/05/2024
Problem: | JS - heap memory space (4140MB), PLC service reaching max heap space within 115 min for 800 tags | Solution: | PM2 configured so that after reaching 100% it automatically restart the plc service only Gateway service not exceeding 100%
Observation: 1.Only plc service getting restart automaticaly by PM2, there is no change in batch 2.Need to check after plc service restarting , time taking to load all tags
Observation of 2 points: During automatic restart(PM2), all tags loaded quickly and no delay(checked on 31/05/2024 )
2024-01-06
Problem: | Kepware to plc communication disconnect - multiple 0 value posting and again reconnected back to original data | Soln:
Observation: multiple 0 posted from 9.28 to 9.34 from zone 3.3 plc 1(3020 to 3110)
Problem: | After pm2 configuration(both service), 31/05/2024 10:54am to 01/06/2024 01:19am data posted. while checking on 01/06/2024 9.00 am both service online, plc service - plc connection true but no tag loaded |  | Yet to discuss
2024-01-06
Problem: | Light curtain error showing machine under error but tower lamp no red colour, instead yellow | Soln: | Err.active should 1 for light curtain error only on production time(AS:true & AR:true) - plc logic modification
2024-03-06
Problem: | Kepware: station machine status working fine after 10 to 15 min la all station machine status showing error active 1 remaining status 0,(observed in zone3(120 to 150)
Video taken on 03/06/2024 and saved in HMCL commissioning folder
2024-05-06
Problem: | Kepware wrong value updating 10 min once in zone 3 plc 2 | progress: | Log files, system application file, kepware diagnostics files send with kepware support team
14/06/2024
Problem: | Frontend building before deloyment ,failed to compile issue | Solution: | If no admin privileage access , create the path which is accessible .Then change the path in code accordinly in package.json file and save.After that only build the frontend .
Problem: | Upload Manual was not working | Solution: | Create a Folder "Manuals" in Publish Folder since it will not be included while Publishing.
| Download Manual not working | Solution: | Added Frontend before Manuals - "/frontend/Manuals/" in Onclick of Download
| Historic Alarm Help Icon ( ? ) Onclick should Download Files | Solution: | Added Frontend before Manuals - "/frontend/Manuals/" in Onclick of Download
| Live Alarm Help Icon ( ? ) Onclick should Download Files | Solution: | Added Frontend before Manuals - "/frontend/Manuals/" in Onclick of Download

## KPI Tag Validations
Sl.No | Zone | Machine Code | Machine name | Machine Description | Production_Count_Reset | Operation_Complete | Break_Timing | OK_Production_Count | NOK_Production_Count | Total_Production_Count | Rework_Count | Active_Mode_Of_Operation | Rejection_BIT | Rejection Reason | Model_Number | Actual_Cycle_Time | Shift_Code | Error_Active | Alarm- WORD | Alarm Description | Loss_BIT | Loss Description
1 | Zone 2 | M1 | HBP1S2020A | Cell Holder Laser Marking Station-1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
2 |  | M2 | HBP1S2040A | Manual Cell Loading Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
3 |  | M3 | HBP1S2045A | module pressing station 1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
4 |  | M4 | HBP1S2045B | module pressing station 2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
5 |  | M5 | HBP1S2050A | Upper Cell Holder Loading Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
6 |  | M6 | HBP1S2050B | Upper Cell Holder Assembly Station 2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
7 |  | M7 | HBP1S2060A | Cell Stack Plasma Cleaning Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
8 |  | M8 | HBP1S2065A | Z Fixation Assembly Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
9 |  | M9 | HBP1S2090A | Heat Stacking Station-1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
10 |  | M10 | HBP1S2100A | Z-Fixation Plasma Cleaning Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
11 | Zone 3.3 | M11 | HBP1S3020A | `+ve Resistance Welding Station -1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
12 |  | M12 | HBP1S3020B | `-ve Resistance Welding Station -1 | Yet to receive | Yet to receive | Received Tag Address Yet to be mapped | Yet to receive | Yet to receive | Yet to receive | Received Tag Address Yet to be mapped | Yet to receive | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Handled in Gateway Working Fine | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive
13 |  | M13 | HBP1S3030A | `+ve Resistance Welding Station -2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
14 |  | M14 | HBP1S3030B | `-ve Resistance Welding Station -2 | Yet to receive | Yet to receive | Received Tag Address Yet to be mapped | Yet to receive | Yet to receive | Yet to receive | Received Tag Address Yet to be mapped | Yet to receive | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Handled in Gateway Working Fine | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive
15 |  | M15 | HBP1S3040A | Welding Integrity Checking Station-1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
16 |  | M16 | HBP1S3050A | Welding Integrity Checking Station-2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
17 |  | M17 | HBP1S3070A | Foam Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
18 |  | M18 | HBP1S3085A | Flipping Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
19 |  | M19 | HBP1S3100A | Thermal Paste Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
20 |  | M20 | HBP1S3110A | BMS Assembly & Activation Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
21 |  | M21 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Validation Completed | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
22 |  | M22 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Validation Completed | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
23 |  | M23 | HBP1S3140A | End Cover Insertion & Glue Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
24 |  | M24 | HBP1S3150A | Leak Testing & Plugging Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Validation Completed | Validation Completed | Validation Completed | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Validation Completed | Yet to receive | Yet to receive | Yet to receive | Yet to receive
25 | Zone 3.4 | M25 | HBP1S4020A | `+ve Resistance Welding Station -1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
26 |  | M26 | HBP1S4020B | `-ve Resistance Welding Station -1 | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Handled in Gateway Working Fine | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive
27 |  | M27 | HBP1S4030A | `+ve Resistance Welding Station -2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
28 |  | M28 | HBP1S4030B | `-ve Resistance Welding Station -2 | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Handled in Gateway Working Fine | Yet to receive | Yet to receive | Yet to receive | Yet to receive | Yet to receive
29 |  | M29 | HBP1S4040A | Welding Integrity Checking Station-1 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
30 |  | M30 | HBP1S4050A | Welding Integrity Checking Station-2 | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
31 |  | M31 | HBP1S4070A | Foam Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
32 |  | M32 | HBP1S4085A | Flipping Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
33 |  | M33 | HBP1S4100A | Thermal Paste Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
34 |  | M34 | HBP1S4110A | BMS Assembly & Activation Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
35 |  | M35 | HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
36 |  | M36 | HBP1S4130A | End Cover Insertion & Glue Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
37 |  | M37 | HBP1S4140A | End Cover Insertion & Glue Dispensing Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive
38 |  | M38 | HBP1S4150A | Leak Testing & Plugging Station | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Received Tag Address Yet to be mapped | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tags Mapping - ( Completed ) Yet to Validate | Received Tag Address Yet to be mapped | Handled in Gateway Working Fine | Received Tags Mapping - ( Completed ) Yet to Validate | Yet to receive | Yet to receive | Yet to receive | Yet to receive

## Akash_KPI Tag Validation
Sl.No | Zone | Machine Code | Machine name | Machine Description | Production_Count_Reset | Operation_Complete | Break_Timing | OK_P_Count | NOK_P_Count | Total_P_Count | Rework_Count | Active_Mode_Of_Operation | Rejection_BIT | Rejection Reason | Model_Number | Target Cycle time(HMI) | Actual_Cycle_Time | Shift_Code | Error_Active | Alarm- WORD | Alarm Description | Loss_BIT | Loss Description
1 | Zone 2 | M1 | HBP1S2020A | Cell Holder Laser Marking Station-1 10-10-2024(11-26 am) | 11:31AM |  | Received Tag Address Yet to be mapped | Ok= 48 | Nok-0 | Total - 48 |  | AS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8P | 822.36 Second | 21.00 Second | Handled in Gateway Working Fine | TRUE | SCADA Comunication Error. | Yet to receive | L1-waiting for pallet reciveding L2-Operator Cycle Start L3-Waiting for Pallete leave | Yet to receive
2 |  | M2 | HBP1S2040A | Manual Cell Loading Station(11:38) | 11:39AM |  | Received Tag Address Yet to be mapped | 8 | 0 | 8 |  | AS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 550.00 Second | 10.8 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
3 |  | M3 | HBP1S2045A | module pressing station 1(11:42 AM) | 11:46AM |  | Received Tag Address Yet to be mapped | 9 | 0 | 0 |  | AS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 774.96 Second | 45.70 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
4 |  | M4 | HBP1S2045B | module pressing station 2(11:44 AM) | 11:46AM |  | Received Tag Address Yet to be mapped | 11 | 0 | 11 |  | MS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 30.00 Second | 3.70 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
5 |  | M5 | HBP1S2050A | Upper Cell Holder Loading Station(11:48Am) | 11:50AM |  | Received Tag Address Yet to be mapped | 47 | 0 | 47 |  | MS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 30.00 Second | 333 Second | Handled in Gateway Working Fine | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
6 |  | M6 | HBP1S2050B | Upper Cell Holder Assembly Station 2(11:50AM) | 11:51AM |  | Received Tag Address Yet to be mapped | 13 | 0 | 13 |  | AS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 0.005 Second | 54.20 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
7 |  | M7 | HBP1S2060A | Cell Stack Plasma Cleaning Station(11:52Am) | 11:53AM |  | Received Tag Address Yet to be mapped | 1 | 0 | 1 |  | MS=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 70.00 Second | 5.0 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1--waiting for pallet reciveding L2 L3 | Yet to receive
8 |  | M8 | HBP1S2065A | Z Fixation Assembly Station | 11:54AM |  | Received Tag Address Yet to be mapped | 1 | 0 | 1 |  | AR = True |  | Received Tags Mapping - ( Completed ) Yet to Validate | 8p | 0.00 Second | 8.10 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
9 |  | M9 | HBP1S2090A | Heat Stacking Station-1 | 0 |  | Received Tag Address Yet to be mapped | 0 | 0 | 0 |  | AS= True |  | Received Tags Mapping - ( Completed ) Yet to Validate | not showing HMI | 180.32 Second | 1.80 Second | Handled in Gateway Working Fine | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
10 |  | M10 | HBP1S2100A | Z-Fixation Plasma Cleaning Station | 0 |  | Received Tag Address Yet to be mapped | 1 | 0 | 1 |  | AR=True |  | Received Tags Mapping - ( Completed ) Yet to Validate | not showing HMI | 60.10 Second | 94.60 Second | Handled in Gateway Working Fine | TRUE |  | Yet to receive | L1- L2- L3- | Yet to receive
11 | Zone 3.3 | M11 | HBP1S3020A | `+ve Resistance Welding Station -1 |  |  |  | 0 | 0 | 0 |  | AR= True |  |  | 8p | 420 Second | 6.1 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
12 |  | M12 | HBP1S3020B | `-ve Resistance Welding Station -1 |  |  |  | 0 | 0 | 0 |  | AR= True |  |  | 8p | 420 Second | 2.00 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
13 |  | M13 | HBP1S3030A | `+ve Resistance Welding Station -2 |  |  |  | 0 | 1 increment | 1 |  | AR= True |  |  | 8p | 420 Second | 423 Second |  | TRUE |  | Yet to receive | L1- waiting for pallet reciveding L2 L3 | Yet to receive
14 |  | M14 | HBP1S3030B | `-ve Resistance Welding Station -2 |  |  |  | 0 | 2 increment | 2 |  | AR= True |  |  | 8p | 420 Second | 413.0 Second |  | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
15 |  | M15 | HBP1S3040A | Welding Integrity Checking Station-1 | 12:40 |  |  | 1 | 0 | 1 |  | AS= True |  |  | 8p | 250 Second | 232.8 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 - waiting for pallet reciveding | Yet to receive
16 |  | M16 | HBP1S3050A | Welding Integrity Checking Station-2 | 12:41 |  |  | 1 | 0 | 1 |  | AS= True |  |  | 8p | 250 Second | 232.8 Second |  | TRUE |  | Yet to receive | L1 - waiting for pallet reciveding L2 L3 | Yet to receive
17 |  | M17 | HBP1S3070A | Foam Dispensing Station |  |  |  | 0 | 0 | 0 |  | ONE(Operation Not enable) |  |  | not showing HMI | 0.00 Second | 159.70 Second |  | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
18 |  | M18 | HBP1S3085A | Flipping Station |  |  |  | 0 | 0 | 0 |  | ONE(Operation Not enable) |  |  | not showing HMI | 49 Second | 37.2 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
19 |  | M19 | HBP1S3100A | Thermal Paste Dispensing Station | 12:47 |  |  | 4 | 0 | 4 |  | ONE(Operation Not enable) |  |  | 9p | 250 Second | 101 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
20 |  | M20 | HBP1S3110A | BMS Assembly & Activation Station |  |  |  | 0 | 0 | 0 |  | ONE(Operation Not enable) |  |  | 7p | 250 Second | 6 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
21 |  | M21 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station |  |  |  | 0 | 0 | 0 |  | AS= True |  |  | 7p | 228 Second | 74.3 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
22 |  | M22 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station | 12:51PM |  |  | 0 | 9 | 0 |  | AS= True |  |  | 7p | 500 Second | 189.9 Second |  |  |  | Yet to receive | L1 L2 L3 | Yet to receive
23 |  | M23 | HBP1S3140A | End Cover Insertion & Glue Dispensing Station |  |  |  | 0 | 0 | 0 |  | AS= True |  |  | 9p | 500 Second | 478 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
24 |  | M24 | HBP1S3150A | Leak Testing & Plugging Station | 12:53PM |  |  | 126 | 8 | 0 |  | AS= True |  |  | not showing HMI | 995 Second | 379.90 Second |  | FALSE |  | Yet to receive | L1 L2 L3 | Yet to receive
25 | Zone 3.4 | M25 | HBP1S4020A | `+ve Resistance Welding Station -1 10-10-24(11:20 to) | 4:10pm |  |  | 4 | 1 | 5 |  | ONE(Operational Not enable) |  |  | 9p | 0.00 Second | 585.90 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
26 |  | M26 | HBP1S4020B | `-ve Resistance Welding Station -1 | 4:10PM |  |  | 10 | 1 | 11 |  | ONE(Operational Not enable) |  |  | 9p | 0.00 Second | 622.10 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
27 |  | M27 | HBP1S4030A | `+ve Resistance Welding Station -2 | 4:10PM |  |  | 1 | 0 | 1 |  | ONE(Operational Not enable) |  |  | 8p | 0.00 Second | 463.0 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
28 |  | M28 | HBP1S4030B | `-ve Resistance Welding Station -2 | 4:11PM |  |  | 1 | 0 | 1 |  | ONE(Operational Not enable) |  |  | 8p | 0.00 Second | 144.50 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
29 |  | M29 | HBP1S4040A | Welding Integrity Checking Station-1 | 4:13PM |  |  | 10 | 0 | 10 |  | ONE(Operational Not enable) |  |  | 8p | 0.00 Second | 108.10 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
30 |  | M30 | HBP1S4050A | Welding Integrity Checking Station-2 | 4:14pm |  |  | 11 | 0 | 11 |  | ONE(Operational Not enable) |  |  | 9p | 0.00 Second | 102.80 Second |  | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
31 |  | M31 | HBP1S4070A | Foam Dispensing Station | 4:15PM |  |  | 5 | 0 | 5 |  | ONE(Operational Not enable) |  |  | 9p | 0.00 Second | 112.00 Second |  | TRUE |  | Yet to receive | L1 L2 L3 | Yet to receive
32 |  | M32 | HBP1S4085A | Flipping Station |  |  |  | 0 | 0 | 0 |  | ONE(Operational Not enable) |  |  | not showing HMI | 0.00 Second | 43.30 Second |  | TRUE | Emegency pressed | Yet to receive | L1 L2 L3 | Yet to receive
33 |  | M33 | HBP1S4100A | Thermal Paste Dispensing Station | 16:19 |  |  | 1 | 0 | 0 |  | MS = True |  |  | 8P | 0.00 Second | 0.00 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive | Total Count Not Showing in HMI.
34 |  | M34 | HBP1S4110A | BMS Assembly & Activation Station | 16:21 |  |  | 11 | 0 | 11 |  | AS = True |  |  | 7P | 0.00 Second | 4.40 Second |  | TRUE | Lab View Communication Error | Yet to receive | L1 L2 L3 | Yet to receive
35 |  | M35 | HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station |  |  |  | 0 | 0 | 0 |  | AR = True |  |  | 8P | 0.00 Second | 119.00 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
36 |  | M36 | HBP1S4130A | End Cover Insertion & Glue Dispensing Station |  |  |  | 0 | 0 | 0 |  | ONE(Operational Not enable) |  |  | 9P | 0.00 Second | 8359.30 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
37 |  | M37 | HBP1S4140A | End Cover Insertion & Glue Dispensing Station |  |  |  | 0 | 10 | 0 |  | ONE(Operational Not enable) |  |  | not showing HMI | 0.00 Second | 0.00 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive
38 |  | M38 | HBP1S4150A | Leak Testing & Plugging Station |  |  |  | 0 | 0 | 0 |  | MS = True |  |  | 0 | 0.00 Second | 272.70 Second |  | TRUE | SCADA Comunication Error. | Yet to receive | L1 L2 L3 | Yet to receive

## 11-10-2024 Validation Report
Sl.No | Zone | M Code | Machine name | Machine Description | OK_P_Count | NOK_P_Count | Total_P_Count | Active_Mode_Of_Operation | Model_Number | Actual_Cycle_Time | Error_Active | Alarm- WORD | Loss_BIT | Production_Count_Reset | Rejection_BIT | Rework_Count | Operation_Complete | Remarks
1 | Zone 2 | M1 | HBP1S2020A | Cell Holder Laser Marking Station-1 10-10-2024(11-26 am) | Ok= 48 | Nok-0 | Total - 48 | AS=True | 8P | 21.00 Second | TRUE | SCADA Comunication Error. | L1-waiting for pallet reciveding L2-Operator Cycle Start L3-Waiting for Pallete leave | 11:31AM
2 |  | M2 | HBP1S2040A | Manual Cell Loading Station(11:38) | 8 | 0 | 8 | AS=True | 8p | 10.8 Second | TRUE |  | L1 L2 L3 | 11:39AM
3 |  | M3 | HBP1S2045A | module pressing station 1(11:42 AM) | 9 | 0 | 0 | AS=True | 8p | 45.70 Second | TRUE |  | L1 L2 L3 | 11:46AM
4 |  | M4 | HBP1S2045B | module pressing station 2(11:44 AM) | 11 | 0 | 11 | MS=True | 8p | 3.70 Second | TRUE |  | L1 L2 L3 | 11:46AM
5 |  | M5 | HBP1S2050A | Upper Cell Holder Loading Station(11:48Am) | 47 | 0 | 47 | MS=True | 8p | 333 Second | TRUE | SCADA Comunication Error. | L1 L2 L3 | 11:50AM
6 |  | M6 | HBP1S2050B | Upper Cell Holder Assembly Station 2(11:50AM) | 13 | 0 | 13 | AS=True | 8p | 54.20 Second | TRUE |  | L1 L2 L3 | 11:51AM
7 |  | M7 | HBP1S2060A | Cell Stack Plasma Cleaning Station(11:52Am) | 1 | 0 | 1 | MS=True | 8p | 5.0 Second | TRUE |  | L1--waiting for pallet reciveding L2 L3 | 11:53AM
8 |  | M8 | HBP1S2065A | Z Fixation Assembly Station | 1 | 0 | 1 | AR = True | 8p | 8.10 Second | TRUE |  | L1 L2 L3 | 11:54AM
9 |  | M9 | HBP1S2090A | Heat Stacking Station-1 | 0 | 0 | 0 | AS= True | not showing HMI | 1.80 Second | TRUE | SCADA Comunication Error. | L1 L2 L3 | 0
10 |  | M10 | HBP1S2100A | Z-Fixation Plasma Cleaning Station | 1 | 0 | 1 | AR=True | not showing HMI | 94.60 Second | TRUE |  | L1- L2- L3- | 0
11 | Zone 3.3 | M11 | HBP1S3020A | `+ve Resistance Welding Station -1 | 0 | 0 | 0 | AR= True | 8p | 6.1 Second |  |  | L1 L2 L3
12 |  | M12 | HBP1S3020B | `-ve Resistance Welding Station -1 | 0 | 0 | 0 | AR= True | 8p | 2.00 Second |  |  | L1 L2 L3
13 |  | M13 | HBP1S3030A | `+ve Resistance Welding Station -2 | 0 | 1 increment | 1 | AR= True | 8p | 423 Second | TRUE |  | L1- waiting for pallet reciveding L2 L3
14 |  | M14 | HBP1S3030B | `-ve Resistance Welding Station -2 | 0 | 2 increment | 2 | AR= True | 8p | 413.0 Second | TRUE |  | L1 L2 L3
15 |  | M15 | HBP1S3040A | Welding Integrity Checking Station-1 | 1 | 0 | 1 | AS= True | 8p | 232.8 Second | TRUE | SCADA Comunication Error. | L1 - waiting for pallet reciveding | 12:40
16 |  | M16 | HBP1S3050A | Welding Integrity Checking Station-2 | 1 | 0 | 1 | AS= True | 8p | 232.8 Second | TRUE |  | L1 - waiting for pallet reciveding L2 L3 | 12:41
17 |  | M17 | HBP1S3070A | Foam Dispensing Station | 0 | 0 | 0 | ONE(Operation Not enable) | not showing HMI | 159.70 Second | TRUE |  | L1 L2 L3
18 |  | M18 | HBP1S3085A | Flipping Station | 0 | 0 | 0 | ONE(Operation Not enable) | not showing HMI | 37.2 Second |  |  | L1 L2 L3
19 |  | M19 | HBP1S3100A | Thermal Paste Dispensing Station | 4 | 0 | 4 | ONE(Operation Not enable) | 9p | 101 Second |  |  | L1 L2 L3 | 12:47
20 |  | M20 | HBP1S3110A | BMS Assembly & Activation Station | 0 | 0 | 0 | ONE(Operation Not enable) | 7p | 6 Second |  |  | L1 L2 L3
21 |  | M21 | HBP1S3120A | Plasma Cleaning & Cell Module Insertion Station | 0 | 0 | 0 | AS= True | 7p | 74.3 Second |  |  | L1 L2 L3
22 |  | M22 | HBP1S3130A | End Cover Insertion & Glue Dispensing Station | 0 | 9 | 0 | AS= True | 7p | 189.9 Second |  |  | L1 L2 L3 | 12:51PM
23 |  | M23 | HBP1S3140A | End Cover Insertion & Glue Dispensing Station | 0 | 0 | 0 | AS= True | 9p | 478 Second | TRUE | SCADA Comunication Error. | L1 L2 L3
24 |  | M24 | HBP1S3150A | Leak Testing & Plugging Station | 126 | 8 | 0 | AS= True | not showing HMI | 379.90 Second | FALSE |  | L1 L2 L3 | 12:53PM
25 | Zone 3.4 | M25 | HBP1S4020A | `+ve Resistance Welding Station -1 | 3 | 0 | [11 empty] | 1.Nok parts mismatch kepware to RawTable.
26 |  | M26 | HBP1S4020B | `-ve Resistance Welding Station -1
27 |  | M27 | HBP1S4030A | `+ve Resistance Welding Station -2
28 |  | M28 | HBP1S4030B | `-ve Resistance Welding Station -2
29 |  | M29 | HBP1S4040A | Welding Integrity Checking Station-1
30 |  | M30 | HBP1S4050A | Welding Integrity Checking Station-2
31 |  | M31 | HBP1S4070A | Foam Dispensing Station
32 |  | M32 | HBP1S4085A | Flipping Station
33 |  | M33 | HBP1S4100A | Thermal Paste Dispensing Station | [13 empty] | Total parts mismatch in HMI.
34 |  | M34 | HBP1S4110A | BMS Assembly & Activation Station
35 |  | M35 | HBP1S4120A | Plasma Cleaning & Cell Module Insertion Station
36 |  | M36 | HBP1S4130A | End Cover Insertion & Glue Dispensing Station
37 |  | M37 | HBP1S4140A | End Cover Insertion & Glue Dispensing Station
38 |  | M38 | HBP1S4150A | Leak Testing & Plugging Station